## Instructions
Instructions for completing the risk tables and risk register
1 | Please use the information included in the Risk Tables tab as a guide for completing the Risk Register.
2 | Capture your risks in the Risks tab. Use the drop-down values to capture the impact and likelihood for each risk before and after mitigation. Note that if you use the CEFF financial model spreadsheet you should scan the "Source or reasoning behind value" column for additional risks.
3 | Revisit your mitigation for any risks with a risk rating of high or extreme.
4 | Identify the person or role responsible to manage each risk.
Disclaimer
This template is set up solely for the purposes of capturing risk information for the Clean Energy Future Fund. It should not be relied upon for any other purpose.

## Risk Tables
Risk Rating
Risk Impact | Impact description | Rating | Description |  | 1 | 2 | 3 | 4 | 5 |  | Risk Impact
| Insignificant | 1 | The risk can result in insignificant impacts including one or more of the following: additional minor costs within budget; first aid injuries; project delays <1 hour; localised, brief low-profile media coverag; no noticeable non-compliance; little impact to agreed milestones or KPIs. |  | Low | Low | Low | Medium | Medium | 1
| Minor | 2 | The risk can result in minor impacts including one or more of the following: additional minor costs within contingency; minor injuries requiring medical attention; project delays <1 day; localised, low-impact, temporary reputational damage; temporary non-compliance; minor variations to agreed milestones or KPIs. |  | Low | Medium | Medium | High | High | 2
| Moderate | 3 | The risk can result in moderate impacts including one or more of the following: additional costs >10% of project value; lost-time injuries; project delays <1 week; temporary reputational damage at the local or regional level; non-compliance with regulatory requirements imposed; variations to agreed milestones or KPIs. |  | Low | Medium | High | High | Extreme | 3
| Major | 4 | The risk can result in major impacts including one or more of the following: additional costs >25% of project value; permanent injury or disability; project delays 1‒4 weeks; widespread reputational damage at the state or regional level; non-compliance resulting in termination of services or penalties; failure to meet an agreed milestone or KPIs. |  | Medium | High | High | Extreme | Extreme | 4
| Catastrophic | 7 | The risk can cause the project to fail, or result in catastrophic impacts including one or more of the following: additional costs >50% of project value; single or multiple fatalities; permanent total disability; project delays >1 month; widespread reputational damage at the national or international level; non-compliance resulting in criminal proceeding; failure to meet multiple agreed milestones or KPIs. |  | Medium | High | Extreme | Extreme | Extreme | 7
Risk Likelihood | Likelihood description | Rating | Description
| Unlikely | 1 | The event has never happened in the organisation or project, but there is a possibility of it occurring at some time under exceptional circumstances. e.g. 0‒10% chance of happening.
| Possible | 2 | The event could and does occur within the organisation or project. e.g. 10‒35% chance of happening.
| Likely | 3 | The event occurs reasonably frequently within the organisation or project. e.g. 35‒65% chance of happening.
| Very Likely | 4 | The event has a very high probability of occurring within the organisation or project. e.g. 65‒90% chance of happening.
| Almost Certain | 5 | The event will almost certainly occur within the organisation or project. e.g. >90% chance of happening.
Risk Rating (Likelihood x Impact) | From | To | Risk Rating | Criteria for risk mitigation strategies
| 0 | 3 | Low | Acceptable with adequate controls. No action required unless level increases.
| 4 | 7 | Medium | May be acceptable with adequate controls. Should be monitored regularly.
| 8 | 14 | High | Unacceptable and must be addressed.
| 15 | 35 | Extreme | Unacceptable and must be addressed.
Note on C7: Ro Richardson: This value is deliberately higher than the sequence in order for catastrophic risks to be rated properly.

## Risk Register
| CEFF RISK REGISTER TEMPLATE |  |  | Project name: | Your project's name
No | Risk description | Risk impact or consequence | Rating before mitigation |  |  | Mitigation | Rating after mitigation |  |  | Risk owner
|  |  | Impact | Likelihood | Rating | Controls to manage the risk | Impact | Likelihood | Rating
| Describe the risk (what event could happen?) | Who/what would it impact, how, and to what extent? | Pick from drop-down | Pick from drop-down | Calculated | What actions will you take to reduce the likelihood or impact of the risk? | Pick from drop-down | Pick from drop-down | Calculated | Who is responsible to manage this risk?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Note: Clear (white) cells are for free text input; cells shaded in light grey feature drop-down selections; blue cells are formulae.