MAC Meeting No 21: 14 July 2009 

[image: image1.jpg]imo-~ .~

Independent Market Operator




Agenda Item 5a (i): Overview of Market Rule Changes
Below is a summary of the status of Market Rule Changes that are either currently being progressed by the IMO or have been registered by the IMO as potential Rule Changes to be progressed in the future.

	Rule changes: Formally submitted (see appendix 1)
	May
	June
	As at 7 July

	Fast track with Consultation Period open
	1
	0
	0

	Standard Rule Changes with 1st Submission Period Open
	5
	2
	2

	Fast Track Rule Changes with Consultation Period Closed (final report being prepared)
	0
	0
	0

	Standard Rule Changes with 1st Submission Period Closed (draft report being prepared)
	3
	6
	4

	Standard Rule Changes with 2nd Submission Period Open
	2
	2
	4

	Standard Rule Changes with 2nd Submission Period Closed (final report being prepared)
	3
	2
	2

	Rule Changes - Awaiting Minister’s Approval and/or Commencement
	0
	1
	0

	Total Rule Changes Currently in Progress
	14
	13
	12

	Potential changes logged by the IMO- Not yet formally submitted (see appendix 2)
	May
	June

	High Priority (to be formally submitted in the next 3/6 months)
	1
	1

(+1/-1)

	Medium Priority (may be submitted in the next 6/12 months)
	10
	13
(+5/-2)

	Low Priority (may be submitted in the next 12/18 months)
	9
	13
(+4)

	Potential Rule Changes (H, M and L)
	20
	27

	Minor and typographical (submitted in batches three times per year)
	16
	17 (+1)


	Total Potential Rule Changes
	36
	44


APPENDIX 1: FORMALLY SUBMITTED RULE CHANGES

Standard Rule Change with First Submission Period Open 

	ID 
	Date submitted 
	Title 
	Submitter 
	Next step 
	Date 

	RC_2009_19
	11/06/2009
	Reserve Capacity Performance Monitoring 
	IMO
	Submission Period Ends
	24/07/2009

	RC_2009_21
	11/06/2009
	Treatment of Negative MCAP on the settlement of Ancillary Services
	Verve Energy
	Submission Period Ends
	24/07/2009


 Standard Rule Change with First Submission Period Closed 
	ID 
	Date submitted 
	Title 
	Submitter 
	Next step 
	Date 

	RC_2009_08 
	21/04/2009
	Updates to Commissioning Provisions
	IMO
	Draft Report Published 
	24/07/2009

	RC_2009_17 
	05/05/2009
	Transparency of Capacity Credit Allocation 
	IMO
	Draft Report Published
	17/07/2009

	RC_2009_18
	05/05/2009
	Reserve Capacity Refund price calculation 
	IMO
	Draft Report Published
	17/07/2009

	RC_2009_20
	05/05/2009
	Opportunistic Maintenance outage approval timeframe   
	System Management
	Draft Report Published
	17/07/2009


 Standard Rule Change with Second Submission Period Open 
	ID 
	Date submitted 
	Title 
	Submitter 
	Next step 
	Date 

	RC_2009_05
	17/03/2009
	Confidentiality of Accepted Outages 
	System Management
	Submission period ends 
	17/07/2009

	RC_2009_10
	21/04/2009
	Early Certified Reserve Capacity
	IMO
	Submission period ends 
	04/08/2009

	RC_2009_11 
	13/03/2009
	Changing the Window of Entry into the Reserve Capacity Market
	IMO
	Submission period ends 
	17/07/2009

	RC_2009_15
	25/03/2009
	Removal of ERA Time Limit to Publish Investigation Results 
	Economic Regulation Authority
	Submission period ends 
	04/08/2009


 Standard Rule Change with Second Submission Period Closed 
	ID 
	Date submitted 
	Title 
	Submitter 
	Next step 
	Date 

	RC_2009_07
	17/03/2009
	Under Construction for the Reserve Capacity Mechanism 
	IMO
	Final Report Published
	17/07/2009

	RC_2009_13
	12/03/2009
	Timing Flexibility for Transfer of Information from System Management
	System Management
	Final Report Published
	17/07/2009


Market Rule Change Overview







Page 2 of 3
 Market Rule Change Overview
                                                                                    
Page 3 of 3



