## Introduction
Climate Risk Assessment Tool (Interim) September 2021
Introduction
Risk assessment criteria
The Climate Risk Assessment Tool has been developed as a template to support WA state agencies and government trading enterprises (GTEs) in completing a climate risk assessment, ongoing identification of risk treatments and implementation of adaptation actions. It can be used where the user’s standard risk registers are not suitable for the purposes of climate risk assessment.
The Tool assists users in structuring their climate risks and enables the rating of risks across multiple future time horizons to consider the long-term impacts climate change is likely to have on the organisation. These time horizons (near-future to 2030 and far-future to 2090) have been selected based on the CSIRO/BOM's Climate Change in Australia projections. Example risks and adaptation actions are provided to assist users in their first pass of risk identification and adaptation planning.
Risk assessment criteria have been provided in an editable form in the Tool to allow users to customise the template with the risk assessment criteria outlined in an organisation's existing enterprise risk management framework/guidance if desired.
This risk assessment tool should be used in conjunction with the guidance and information outline in the:
- Climate Risk Assessment Guide (Interim) - Sept 2021
- Western Australian Climate Projections - Sept 2021
Before beginning the climate risk assessment process, it is recommended to review your organisation's existing enterprise risk management framework as there may be the opportunity for it to be enhanced to better capture the impacts of climate change, enabling consistent consideration of risks by decision-makers.
Tab 2 of the Tool is prefilled with likelihood and consequence criteria outlined by the Australian Greenhouse Office (AGO 2006) and Climate Compass (CSIRO 2018). The values within each of the tables are editable to enable the inclusion of risk criteria outlined by your organisation's enterprise risk management framework. In the absence of suitable risk criteria, use of the prefilled criteria is recommended. Table 2 and Table 3 are editable, and any changes to the headings and contents will automatically carry over to the risk register template. Please note that the order will need to remain the same within the tables (i.e. from highest to lowest likelihood and consequence).
Similarly, the risk matrix can also be updated directly if the example likelihood and consequence combinations do not result in the same rating of risk according to your organisation's enterprise risk management framework (to confirm). If your table has fewer rows/columns than the 5x5 matrix (Table 3), please fill in the existing table starting in the first row and column.
Refer to Step 2 of the Interim Climate Risk Assessment Guide for futher information on undertaking a climate risk assessment for your organisation.

## Risk Criteria
Risk assessment criteria
The below tables are editable to allow you to customise this template with the risk assessment criteria outlined in your organisation's enterprise risk management framework/guidance.
Table 1: Likelihood criteria |  |  |  |  | Table 2: Consequence criteria
Likelihood that a given scenario arises |  |  |  |  | Example consequence scales for a local authority
Rating |  | Recurrent risks | Single events |  | Consequence and success criteria | Public safety | Local growth and economy | Community and lifestyle | Environment and sustainability | Public administration | Enter if required | Enter if required
Almost certain |  | Could occur several times per year | More likely than not – probability greater than 50% |  | Catastrophic | Large numbers of serious injuries or loss of lives | Regional decline leading to widespread business failure, loss of employment and hardship | The region would be seen as very unattractive, moribund and unable to support its community | Major widespread loss of environmental amenity and progressive irrecoverable environmental damage | Public administration would fall into decay and cease to be effective | Enter if required | Enter if required
Likely |  | May arise about once per year | As likely as not – 50/50 chance |  | Major | Isolated instances of serious injuries or loss of lives | Regional stagnation such that businesses are unable to thrive and employment does not keep pace with population growth | Severe and widespread decline in services and quality of life within the community | Severe loss of environmental amenity and a danger of continuing environmental damage | Public administration would struggle to remain effective and would be seen to be in danger of failing completely | Enter if required | Enter if required
Possible |  | May arise once in 10 years | Less likely than not but still appreciable – probability less than 50% but still quite high |  | Moderate | Small numbers of injuries | Significant general reduction in economic performance relative to current forecasts | General appreciable decline in services | Isolated but significant instances of environmental damage that might be reversed with intensive efforts | Public administration would be under severe pressure on several fronts | Enter if required | Enter if required
Unlikely |  | May arise once in 10 to 25 years | Unlikely but not negligible – probability low but noticeably greater than zero |  | Minor | Serious near misses or minor injuries | Individually significant but isolated areas of reduction in economic performance relative to current forecasts | Isolated but noticeable examples of decline in services | Minor instances of environmental damage that could be reversed | Isolated instances of public administration being under severe pressure | Enter if required | Enter if required
Rare |  | Unlikely during the next 25 years | Negligible – probability very small, close to zero |  | Insignificant | Appearance of a threat but no actual harm | Minor shortfall relative to current forecasts | There would be minor areas in which the region was unable to maintain its current services | No environmental damage | There would be minor instances of public administration being under more than usual stress but it could be managed | Enter if required | Enter if required
*prefilled based on Table 11 of Climate change impact and risk management - A guide for business and government (Australian Greenhouse Office 2006) |  |  |  |  | *prefilled based on Table 8 of Climate change impact and risk management - A guide for business and government (Australian Greenhouse Office 2006)
Table 3: Risk matrix | [7 empty] | Table 4 - Control effectiveness
|  | Consequence | [6 empty] | Description and further action
| Select | Insignificant | Minor | Moderate | Major | Catastrophic |  | Substantially effective | Existing controls address risk, are in operation and are applied consistently. Management is confident that the controls are effective and reliable. Ongoing monitoring is required.
Likelihood | Almost certain | Medium | Medium | High | Extreme | Extreme
| Likely | Low | Medium | High | High | Extreme |  | Partially effective | Controls are only partially effective, require ongoing monitoring and may need to be redesigned, improved or supplemented.
| Possible | Low | Medium | Medium | High | High
| Unlikely | Low | Low | Medium | Medium | Medium |  | Largely ineffective | Management cannot be confident that any degree of risk modification is being achieved. Controls need to be redesigned.
| Rare | Low | Low | Low | Low | Medium
| *prefilled based on Table 7 of Climate Compass (CSIRO 2018) | [7 empty] | *prefilled based on Table 4.6 of TPP12-03b (NSW Treasury 2012)
Please do not edit
| Rating result | Effectiveness | Hazards y/n | Consequence | Likelihood
|  |  |  | Select | Select
|  | Select |  | Catastrophic | Almost certain
| Select | Substantially effective |  | Major | Likely
| Extreme | Partially effective |  | Moderate | Possible
| High | Largely ineffective |  | Minor | Unlikely
| Medium |  |  | Insignificant | Rare
Low

## Risk Register
Risk Register
| Risk Register Owner Name: | [7 empty] | Updated by Name:
| Risk Register Owner Position Name: | [7 empty] | Last Update Date:
| Risk description | Business area/Risk owner | Date last assessed DD/MM/YY |  | Natural hazards (climate related) | [7 empty] | Worst case risk rating based on 2030 climate change projections |  |  | Worst case risk rating based on 2090 climate change projections |  |  | Existing Controls |  | Risk Treatment Options
Risk ID |  |  |  | Risk category | Sea level rise & coastal flooding | Mean temperature | Heatwaves/extreme heat days | Relative humidity | Bushfires | Extreme rainfall and flooding | Extreme storms (incl wind & hail) | Droughts | Likelihood | Consequence | Risk rating | Likelihood | Consequence | Risk rating | Controls & treatments (existing) | Control effectiveness for 2030 period | Proposed treatments (adaptation actions) | Residual risk level 2031 | Review and reporting requirements | Comments
Unique identifier | Refer to Guidance for advice on developing a climate risk statement, or refer to the Example Risks tab | Who is responsible for managing the risk |  | e.g. financial, service delivery, work health and safety. Note: your organisation may have different categories. | e.g. map against natural hazards to help understand how many risks relate to specific natural hazards and/or identify any gaps | [7 empty] | The risk if the current control strategy fails completely, based on the risk assessment criteria outlined by your organisation's enterprise risk management framework/guidance |  |  | The risk if the current control strategy fails completely, based on the risk assessment criteria outlined by your organisation's enterprise risk management framework/guidance |  |  | Current controls | Select level of effectiveness from drop-down list | Additional control if risk is not acceptable. Refer to Example adaptation actions tab | Expected level of risk remaining after adaptation actions are implemented | How and when the risk and controls are to be reviewed and reported | Uncertainties or sensitivities; potenital impact on organisational objectives; resources required (financial, physical, human resources, knowledge)
1 | EXAMPLE Increased number of health issues related to heat stress in the workplace due to higher temperatures and increased severity of heatwaves. | Operations | 2019-09-20 |  |  |  |  |  |  |  |  |  | Possible | Minor | Medium | Likely | Moderate | High | Upgrade of building HVAC undertaken in 2018; shading and fans provided in outdoor areas | Substantially effective | Heat stress communications and corporate awareness to be embedded in corporate OSH by 2022 | Medium | Embed in corporate risk register and OSH Strategic Plan. Review as part of annual strategic planning process
2 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
3 | User input | User input | DD/MM/YY | [5 empty] |  |  |  |  | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
4 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
5 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
6 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
7 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
8 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
9 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
10 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
11 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
12 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
13 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
14 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
15 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
16 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
17 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
18 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
19 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
20 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
21 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
22 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
23 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
24 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
25 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
26 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
27 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
28 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
29 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
30 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
31 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
32 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
33 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
34 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
35 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
36 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
37 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
38 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
39 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
40 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
41 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
42 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input
43 | User input | User input | DD/MM/YY | [9 empty] | Select | Select | N/A | Select | Select | N/A | User input | Select |  | Select |  | User input

## Example risks
Example risks, by climate hazard
Consider how climate change will impact the ability of the organisation to deliver against organisation objectives.
Changes to mean temperature will result in…
increased energy and water demand across the site
higher frequency HVAC (Heating, Ventilation, Air Conditioning) system replacement requirements increased need to cool buildings or work sites
increased stress on vital equipment and services (e.g. elevators and plant) leading to greater maintenance demands
greater instances of superficial peeling, cracking, corrosion, etc. to facades including glazing and cladding, structures and surfaces
greater instances of material degradation to facades, structures and surfaces
impacts to landscaping and plantings
impacts to the thermal performance levels of buildings leading to reduced comfort levels for building occupants (e.g. tenants, customers, visitors, etc.)
a reduction in the use of outdoor recreational spaces and amenities
an increase in the urban heat island effect impacting comfort and amenity of outdoor areas
increased pressure across the energy network leading to an increase in energy network instability (e.g. brownouts and blackouts)
higher evaporation rates of water storage sites
increased water contamination and algae blooms
decreased agricultural and regional productiivity
greater failure of transport infrastructure
Changes in the number of extreme heat days and heatwaves will result in….
increased instances of heat stress for building occupants (e.g. tenants, customers, visitors, etc.), particularly vulnerable groups
more frequent heat stress/solar exposure of outdoor building users/staff resulting in health impacts or decreased productivity
increased demand for outdoor respite and refuge areas resulting in insufficient capacity
increased instances of energy and telecommunications network failure (e.g. blackouts/brownouts, etc.) impacting business operations and activities
imapcts to the transport network (as a result of energy and telecommunications network failure) causing staff delays and reducing accessibility to building
an exacerbation of urban heat island effects impacting comfort and amenity
increased energy and water demand across the site
increased demand on the building as a potential area of respite
increased incidence of complaints and/or antisocial behaviour
greater demand for community services and emergency services (e.g. increased mental health impacts)
increased public health risk for recreational activities and events
loss of biodiversity and ecosystem function (e.g. extreme heat mortality)
Increasing frequency and intensity of bushfires will result in….
reduced air quality within open space areas and increase health impacts
reduced air quality within internal areas
smoke and embers impacting ventilation and air-conditioning systems
internal smoke damage as a result of unsealed areas
an accumulation of ash in roof drainage
full or partial fire damage to buildings and public spaces
increased instances of energy and telecommunications network failure impacting business operations and activities
impacts to the transport network causing staff delays and reducing accessibility to building
increased demand on the building as a designated 'safer place' or evacuation centre
damage to infrastructure and assets that deliver public services (e.g. buildings, telecommunications)
increased demand on emergency services
loss of biodiversity
loss of life/injury and increased hospital presentations
higher levels of water contamination (e.g. ash or fire retardent entering waterways)
loss of cultural heritage sites
Changes to relative humidity will result in….
build-up of mould and condensation leading to increased operations and maintenance requirements and costs
changes in relative humidity resulting in decreasing thermal comfort resulting in health impacts or decreased productivity
impacts to the spread of water-borne diseases and distribution of pest species
accelerated carbonation of concrete structures
increased energy demand across the site
Changes to mean rainfall (incl. drought) patterns will result in….
degraded building foundations and other below-ground infrastructure (e.g. wiring) as a result of decreased soil moisture
degraded integrity of building materials (e.g. adhesives, wiring) as a result of warmer and drier conditions
decreased availability of potable water for irrigation
impacts to the spread of water-borne diseases and distribution of pest species
increased incidence of mental health presentations in drought or flood
low runoff impacting environmental flows and biodiversity
decrease in cultural practice in waterways
higher levels of water contamination and algae
loss of farming productivity and increase in financial support
damage to infrastructure and assets (e.g. buildings, telecommunications)
increased instances of energy and telecommunications network failure impacting business operations and activities
Changes in sea level and the frequency of coastal erosion and inundation events will result in….
increased levels of localised flooding due to storm surge limiting access and egress
more frequent and higher storm surges leading to damage to coastal assets and higher maintenance costs
increased frequency of tidal inundation leading to coastal erosion
drainage capacity issues for buildings and hard landscaping
corrosion of exterior infrastructure from salt spray (e.g. concrete)
saltwater intrusion, contaminating water sources, impacting groundwater resources and landscaping, and/or increasing degradation of building materials (e.g. foundations)
limited access and egress as result of permanent inundation of certain areas
increased planning controls to manage associated impacts (e.g. changes to development approvals/conditions, etc.)
damage to infrastructure and assets (e.g. buildings, telecommunications)
Changes in the frequency and intensity of extreme storms (incl. wind and hail) will result in….
increased storm and hail damage to building structure, façade and/or landscaping
increased storm and hail damage to utilities, services and critical plant
increased levels of rain/moisture penetration
increased safety issues for customers/patrons, tenants and staff (including operations and maintenance staff)
increased instances of energy and telecommunications network failure impacting business operations and activities
impacts to the transport network causing staff delays and reducing accessibility to building
increased demand on the building as a place of refuge and/or as a designated evacuation centre
high wind loads on building structure, and increased rainfall and flooding
greater strain or loss of building fixtures, fittings and fastenings
damage from unsecured debris
structural damage due to greater wind load being exerted on asset
additional demand/delays in the emergency service network leading to exacerbated impacts (e.g. injury, stranding) to building occupants or users (e.g. tenants, customers, visitors, etc.)
increased instances of energy and telecommunications network failure impacting business operations and activities
impacts to the transport network causing staff delays and reducing accessibility to building
increased demand on the building as a place of refuge and/or as a designated evacuation centre

## Example adaptation actions
Example adaptation actions
Consider what success looks like in your organisation.
Building organisational adaptive capacity...
Update existing design guidelines to identify and highlight various actions that contribute to sustainability and resilience outcomes.
Work with the executive team to champion the creation of a climate change resilience subcommittee to help drive leadership in climate risk and sustainability and raise the internal profile of the climate risk agenda.
Collaborate to support the creation and use of new project screening procedures to better enable climate change risk and resilience to be embedded into all stages of project delivery.
Encourage staff to develop new methods of reporting up to the leadership team and board, recognising staff for climate change resilience achievements.
Include members of sustainability teams as part of the contract and tender review process.
Within the annual business planning and quarterly reporting activities there is opportunity to have a line item to discuss how climate change risk is assessed.
Review training and materials to provide a climate change induction package for delivery to new starters. Various material formats and/or media are recommended to support efficient information dissemination.
Undertake comprehensive review of the enterprise risk management framework including corporate, strategic and project risks register to embed criteria related to climate risk (as a minimum).
Build capacity of executive levels and the board on climate risks and adaptation through regular briefings
Establish an external facing advocacy position regarding transition risks, in line with peers and partners.
Establish an internal framework for informing decision-making for future planning, leveraging risk management processes, and supported by ongoing monitoring and evaluation.
Asset management and critical infrastructure…
Complete a review of asset management plans to identify opportunities for embedding climate change risk
Develop an asset-wide drainage strategy with consideration of implications for neighbouring communities.
Develop a set of consistent design standards that are integrated into tendering, providing consistent minimum standards for climate adaptation and alignment to capital spend thresholds.
Consider reviewing and updating existing sustainability targets and reporting metrics to increase the number of stretch targets to drive innovation
Develop and implement a monitoring program to understand the performance of past projects and use the findings to inform future developments, e.g. compare projects that were undertaken prior to climate targets/strategy with those completed after.
Adopt the Climate Risk Assessment & Adaptation Plan confirms executive sponsorship and measures implementation on an annual basis.
Review infrastructure design parameters around water capture to cope with increased intensity of rainfall, eg. retention areas to utilise stormwater during dry periods, sustainable stormwater management.
Review asset management plans to identify vulnerable essential services (e.g. transport, telecommunications and water infrastructure) and determine assets at risk from climate hazards.
Safeguard communications infrastructure against extreme heat and bushfire.
Ensure appropriate design for new buildings (e.g. solar design features such as properly shaded north- and west-facing windows, minimal west-facing windows, or provision for effective ventilation).
Build innovative and effective housing and infrastructure that has capacity to withstand flooding.
Strategy and planning…
Review existing masterplans and leverage opportunities to increase climate resilience (e.g. an energy masterplan, construction and upgrade projects).
Influence corporate planning and strategy to consider responses to transition risks and opportunities.
Liaise with insurers to demonstrate proactive measures to reduce flood risk and other material climate impacts.
Develop an urban heat strategy – accounting for operational impacts including increased demand for pre-conditioned air and the development of a program of surface treatment works to reduce urban heat island effects.
Review species selection through the review of the Natural Area Plan of Management.
Identify thresholds for unacceptable change into Natural Area Management plans.
Develop an Asset Management Plan for Natural Areas to manage risks from bushfire, flooding, extreme heat and drying periods.
Seek long-term investment options in the region based on a strategy that integrates productivity and landscape resilience.
Incorporate sea level rise risk into coastal infrastructure planning.
Emergency management and business continuity…
Review existing emergency and operational management plans to ensure they adequately address future spread of communicable diseases.
Develop a climate event scenario and integrate responses to this scenario into the existing Emergency Management Plan, including opportunities to partner with external stakeholders.
Increase staff capacity to support during crises and work with first responders to review access to assets.
Seek ongoing improvements in the accuracy of flood warning systems design.
Examine new ways to incentivise private sector employers to release emergency management workers during extreme events, that recognise the constraints on small business and the self-employed.
Shared risk management and collaboration...
Explore opportunities to partner with industry to develop a thought leadership piece that clearly explores the sustainability and climate resilience in the organisation's sector.
Continue to work with critical infrastructure and service providers to understand system interdependencies and develop an action plan to minimise the duration and frequency of disruptions - including interface between review of essential and non-essential power supplies and transport access/egress.
Develop community adaptation and response plans to build household resilience to natural hazards.
Staff health and wellbeing...
Provide shade/water bottle filling stations within high traffic areas.
Prepare a heatwave or extreme heat response plan.
Investigate flexible working conditions to allow staff to vary work hours to accommodate extreme events.
Develop an internal emergency response strategy to define staff roles and responsibilities during an emergency and in the recovery phase.
Seek greater support from regional businesses for training in climate change adaptation.