## WEM Procedure List
Date Published: | 2022-08-26
AEMO has prepared this preliminary document to provide information about AEMO's WEM Procedures and proposed WEM Procedure timelines, based on the information available to AEMO as at the date of the document. This document or the information in it may not be accurate or complete and may be subsequently updated or amended. AEMO has made every effort to ensure the quality of the information in this document but cannot guarantee its accuracy or completeness. For a forward plan of when WRIG WEM Procedure topic discussions will take place, please refer to the WEM Procedure Schedule within the latest WRIG meeting slides.
Procedure Name | Procedure HoP | Topic | New/ Re-write /Update | Size of change (L, M, S) | Date Topic taken to WRIG | Est. Completion of Topic Discussions | Est. Consultation Date | Est. WEM Procedure Publication (Provisional or Final) | Date Published on AEMO's Website
WEM Procedure: Limit Advice Requirements | 2.27A.10 | Thermal Limit Advice Requirements | New | M | 2020-10-01 | Complete | Closed - 12/10/2020 | 2023-05-24
Non-Thermal Limit Advice Requirements
Non-Thermal Limit Advice Review
WEM Procedure: Constraint Formulation | 2.27A.10; | Standard Methodology for Constraint Equations | New | L | 2020-10-01 | Complete | Closed - 12/10/2020 | 2023-05-24
Development
Operating Margins
Network Constraint Formulation
The Constraint Library
Special Constraints
Constraint Naming
Quality Control
WEM Procedure: Congestion Information Resource | 2.27B.8 | Congestion information Resource | New | S | 2020-10-29 | Complete | Closed - 19/11/2020 | 2023-05-24
Information to be Provided by Network Generators
WEM Procedure: Generator Monitoring Plans (First Revision) | 1.41.6; 3A.6.2 3A.9.1. | Template Generator Monitoring Plan | New | L | 2020-11-26 | Complete | Closed - 11/12/2020 | Complete | 2021-02-01
Compliance Testing and Monitoring Requirements
Submissions, Assessment and Approval Process
Existing Transmission Connected Generating Systems
Non-Compliance with Generator Monitoring Plan
WEM Procedure: Generator Monitoring Plans (Second Revision) | 1.41.6; 3A.6.2 3A.9.1. | Template Generator Monitoring Plan | New | L | 2022-07-28 | Complete | 2022-11-01 | 2023-01-19
Compliance Testing and Monitoring Requirements
Submissions, Assessment and Approval Process
Existing Transmission Connected Generating Systems
Non-Compliance with Generator Monitoring Plan
WEM Procedure: Credible Contingency Events (First Revision) | 3.8A.4 | Contingency Event Framework | New | S | 2020-12-17 | Complete | Closed - 18/01/2021 | Complete | 2021-02-01
WEM Procedure: Credible Contingency Events (Second Revision) | 3.8A.4 | Contingency Event Framework | New | S | 2021-05-27 | Complete | Closed - 25/6/2021 | Complete | 2021-07-29
WEM Procedure: Frequency Co-Optimised Essential System Services Accreditation | 2.34A.13; | Transitional Accreditation for the Provision of ESS | New | L | 1/10/2020 02/09/2021 | Complete | Closed - 09/09/2021 | Complete | 2021-10-01
Accreditation Methodology for ESS Providers
RoCoF Ride Through Capability
Settlement Exemption Process (contingency, Rocof)
WEM Procedure: SESSM Procurement | 3.11.4; 3.15A.46 | SESSM Procurement Methodology | New | M |  | 2023-02-09 | 2023-03-03 | 2023-05-10
SESSM Procurement Trigger
WEM Procedure: ESS Quantity Determination Methodology | 3.11.7 | ESS Quantity Determination Methodology | New | M | 2022-06-30 | 2022-10-13 | 2022-11-03 | 2023-01-23
WEM Procedure: Communications and Control Systems | 2.36A.5; 2.35.4; | Communications and Control - IT Systems | Update | M | 25/03/2021 29/04/2021 | Complete | Closed - 15/09/2021 | Complete | 2021-10-01
|  | Communications and Control - Backup processes | New
Communications and Control - Recording requirements
Communications Standard
SCADA point requirements (generators, networks)
WEM Procedure: IMS Interface for Network Operators | 2.36.7 | Transfer of Information | Update | M |  | 2023-04-27 | 2023-05-09 | 2023-07-14
|  | Technical and Communication Criteria | New
|  | Rule Participant registration exemption | New
WEM Procedure: Monitoring and Reporting Dispatch Compliance | 2.13.19; 7.10.5; 7.10.21. | Facility Tolerance for Dispatch Compliance | Update | M |  | 2023-03-09 | 2023-04-07 | 2023-06-14
Monitoring and Compliance
WEM Procedure: Notices and Communications | 1.6.2 (existing); 3.5.1A; 7.11.8 | Guidelines for Dispatch based Advisories | New | M |  | 2022-09-22 | 2022-10-24 | 2023-01-11
Guidelines for Market based Market Advisories
Guidelines for any other communication
Declaring Emergency Operating States
WEM Procedure: Real-Time Market Timetable | 7.1.2(a) | Real-Time Market Timetable | New | S | 2022-08-23 | Complete | 2022-09-19 | 2022-11-24
WEM Procedure: Price determination | 7.11C.1; 7.11C.11 | Energy Price Determination | New | M |  | 2022-11-24 | 2022-12-20 | 2023-03-09
ESS Price Determination
WEM Procedure: Dispatch Engine Formulation | 7.2.5 | Formulation | New | L |  | 2022-10-27 | 2022-11-10 | 2023-01-30
ESS Factors
Inflexibility Profiles
Infeasibility outcomes
Unavailability outcomes
WEM Procedure: Real-Time Market Submissions | 7.4.20; 7.4.22; 7.4.38; 7.4.62 | Submission Type | New | L | 2021-09-30 | 2022-09-08 | 2022-11-02 | 2023-01-20
Submission Process
Submission Format
Validation
Standing Conversion
Acceptance/Acknowledgement
WEM Procedure: Adjustment of Essential System Service Parameters for Dispatch | 7.4.53 | Scaling ESS Trapezia to Technical Limits | New | M |  | 2022-11-11 | 2022-11-24 | 2023-02-13
Application of ESS Trapezia scaling to Market Schedules
WEM Procedure: Facility Dispatch Process | 7.2.8; 7.3.4; 7.4.53; 7.5.4; 7.6.3; 7.6.18; 7.6.27; 7.6.33; 7.7.14; 7.8.9; 7.13.5; 7.13.3; 7.13.8. | Dispatch Communication Process (issue, acknowledge) | Update | L |  | 2023-01-26 | 2023-02-28 | 2023-05-05
Dispatch Conversion
Dispatch Override
DSP Dispatch
Constraint Relaxation
Invoking Constraints
Forecast Operational Demand
WEM Procedure: Dispatch Settlement and Monitoring Data | 7.13.3; 7.13.5; 7.13.8 | Settlement and Monitoring Data | New | M |  | 2022-11-24 | 2023-01-09 | 2023-03-16
Decrease in Consumption for DSP Calculation
Estimation of max quantity of sent out energy for intermittent components of Semi-Scheduled Facilities
WEM Procedure: Outages | 3.18.4; 3.19.11; 3.21.10; 3.21.17 (Outage RC). | Outage Intention Plan (OIP) | New | L | 2022-06-30 | 2022-10-27 | 2022-11-02 | 2023-01-20
Outage Submission (including by component, type)
|  | Outage Coordination/Prioritisation | Update
|  | Outage Evaluation/Approval | New
Outage Revisions
Outage Quantity Determination
Intermittent Load - Generation outage process
Outage Compensation
WEM Procedure: Reliability Standard Implementation | 3.3.2 | Processes for managing Reliability | New | M |  | 2022-12-08 | 2023-02-01 | 2023-04-10
WEM Procedure: ST PASA | 3.16.10 | PASA Reporting | Update | M | 2021-06-24 | 2023-03-30 | 2023-04-25 | 2023-07-01
WEM Procedure: MT PASA | 3.16.10 | PASA Reporting | Update | M | 2021-06-24 | 2022-12-08 | 2023-02-01 | 2023-04-10
WEM Procedure: Low Reserve Conditions | 3.17.11 | PASA Low Reserve Planning | New | M |  | 2023-02-09 | 2023-03-03 | 2023-05-10
WEM Procedure: Power System Security | 3.2.7; 3.2.2 | Determination of the Technical Envelope | New | L |  | 2022-10-13 | 2022-11-17 | 2023-02-06
Delivery and treatment of Equipment Limits
Power System Stability (including System Strength)
Inertia Requirements
WEM Procedure: Commissioning Tests | 3.21A.27 | Submission Process | Update | M |  | 2023-02-23 | 2023-03-24 | 2023-06-01
Timeline
Submission format
Validation
Approval
Rescheduling
WEM Procedure: Certification of Reserve Capacity | 4.9.10; 4.10A.11; 4.28C.15. | Degradation of ESR | Update | L |  | 2023-06-29 | 2023-07-25 | 2023-10-01
Certification of Hybrid Facilities
Unassessable technology combinations
Certification of Facility/Technology classes
Independent Expert Reports
Outages Rule Change RC_2014_03
RLM Rule Change RC_2019_03
Early Certification
Certification of upgrades
Network Augmentation Funding Facilities
Firm and Non-Firm Fuel Type
WEM Procedure: Certification of Reserve Capacity for the 2021 Reserve Capacity Cycle | 4.9.10; 4.28C.15. | Degradation of ESR | New | L | 05/08/2021 02/09/2021 | Complete | Closed - 22/09/2021 | Complete | 2021-10-29
Certification of Hybrid Facilities
Unassessable technology combinations
Certification of Facility/Technology classes
Independent Expert Reports
Outages Rule Change RC_2014_03
RLM Rule Change RC_2019_03
Early Certification
Certification of upgrades
WEM Procedure: Certification of Reserve Capacity for the 2022 and 2023 Reserve Capacity Cycles | 4.9.10; 4.10A.11; 4.28C.15. | Degradation of ESR | New | L | 2021-11-25 | Complete | Closed - 28/01/2022 | Complete | 2022-03-01
Certification of Hybrid Facilities
Unassessable technology combinations
Certification of Facility/Technology classes
Independent Expert Reports
Outages Rule Change RC_2014_03
RLM Rule Change RC_2019_03
Early Certification
Certification of upgrades
Network Augmentation Funding Facilities
WEM Procedure: Transitional RCM Constraint Formulation | 2.27A.10 | NAQ required Constraints | New | M | 2022-02-24 | Complete | Closed - 13/06/2022 | 2022-09-09
WEM Procedure: Transitional RCM Limit Advice Requirements | 2.27A.10 | RCM Limit Advice | New | M | 2022-01-27 | Complete | Closed - 24/01/2022 | Complete | 2022-03-11
WEM Procedure: Assignment of NAQs | 4.15.17 | NAQ Model | New | L |  | 2022-11-11 | 2022-12-12 | 2023-03-01
Facility Dispatch Scenarios Determination
Determining NAQ
WEM Procedure: ESR obligation intervals | 4.11.3A(c) | Defining ESR obligation intervals | New | M | 2021-03-25 | Complete | Closed - 03/05/2021 | Complete | 2021-07-11
Moving of ESR obligation intervals
WEM Procedure: Declaration of Bilateral Trades for the 2021 Reserve Capacity Cycle | 4.14.11 | Clarification of nominating for price | Update | M | 2021-10-28 | Complete | Closed - 19/01/2022 | Complete | 2022-03-01
Existing procedure content
WEM Procedure: Declaration of Bilateral Trades | 4.14.11 | Clarification of nominating for price | Update | M | 2022-06-09 | Complete | Closed - 13/06/2022 | 2022-09-01
Existing procedure content
WEM Procedure: Supplementary Reserve Capacity | 4.24.18 | Acquiring Eligible Services | Update | S |  | 2023-03-30 | 2023-04-13 | 2023-06-19
Entering into Supplementary Capacity Contracts
Determining maximum contract value per hour of availability
Supplementary Capacity payments for parties who aren't a Market Participant
Determining a provider of an Eligible Service has access to the network
WEM Procedure: Reserve Capacity Security Procedure | 4.13.8; 4.13A.23 | Determining Reserve Capacity Security | Update | S |  | 2023-03-30 | 2023-04-13 | 2023-06-19
Acceptable Credit Criteria assessments
Reserve Capacity Secuirty arrangements
WEM Procedure: Reserve Capacity Performance Monitoring | 4.27.12 | Perfomance Monitoring | Update | S |  | 2023-03-30 | 2023-04-13 | 2023-06-19
|  | Performance Reports | Update
WEM Procedure: Consumption Deviation Applications | 4.26.2CE; 4.28.9E. | Relevent Demand | Update | S |  | 2023-03-30 | 2023-04-13 | 2023-06-19
NTDL
WEM Procedure: Undertaking the Long Term PASA | 4.5.14 | Undertaking the Long Term PASA | Update | M | 2022-04-28 | Complete | Closed - 13/05/2022 | 2022-09-16
WEM Procedure: Reserve Capacity Testing | 4.25.14 | Testing Requirements (inc re-testing) | Update | L |  | 2023-04-13 | 2023-05-19 | 2023-07-26
DSP Testing
Hybrid Facility Testing
Non-Hybrid Facility Testing
ESR Component Testing
WEM Procedure: Facility Sub-Metering (First Revision) | 2.29.15 | Facility Sub-Metering standards | New | L | 2021-03-25 | Complete | Closed - 03/06/2021 | Complete | 2021-07-01
Facility Sub-Metering usage in RCM
WEM Procedure: Facility Sub-Metering (Second Revision) | 2.29.15 | Facility Sub-Metering standards | New | L | 2021-10-28 | Complete | Closed - 08/11/2021 | Complete | 2021-12-01
Facility Sub-Metering usage in RCM
WEM Procedure: Rule Participant Registration and Deregistration Process | 2.31.25(a) | Rule Participant Registration | Update | L |  | 2022-12-08 | 2023-02-01 | 2023-04-10
Rule Participant Deregistration
Rule Participant Exemption
WEM Procedure: Facility registration, de-registration and transfer Procedure | 2.29.4N; 2.29.5N; 2.29.9; 2.30.11; 2.31.25(b); 2.31.25(c); 2.31.25(d) | DSP association by TNI/Electrical Location | Update | L |  | 2022-12-08 | 2023-02-01 | 2023-04-10
Dealing with GPS (monitoring plans, outstanding non-compliance)
Facility Aggregation and Disaggregation
Standing Data Requirements
Monitoring of Registration Compliance
Determination of Electrical Location
Controllability Assessment for Dispatch
Controllability Assessment for RCM
WEM Procedure: Network Modelling Data | 2.28.20 | Network Modelling Data Provision | Update | S |  | 2022-11-11 | 2022-11-29 | 2023-02-15
WEM Procedure: Meter Data Submission Procedure | 8.6.2 | Meter Data Submission format | Update | M |  | 2023-01-26 | 2023-02-22 | 2023-05-01
WEM Procedure: Settlements | 9.2.1; 9.2.2; 4.28A.3 | Settlement Process | Update | M |  | 2023-01-26 | 2023-02-22 | 2023-05-01
Uplift Payment methodology
Estimation of Facility capacity for ESS
Intermittent Load Refunds - Generation outage refunds
Financial Penalty Distribution Process
WEM Procedure: Capacity Credit Allocations | 4.30.12 | Daily Allocation process | Update | M | 2022-11-25 | Complete | Closed - 4/03/2022 | Complete | Final draft 09/06/2022
WEM Procedure: Individual Reserve Capacity Requirements (IRCR) | 4.28.12 | IRCR Methodology | Update | S |  | 2023-02-23 | 2023-02-23 | 2023-05-01
Consideration of ESR contribution
WEM Procedure: Prudential Requirements | 2.43.1 | Credit Limits | Update | S |  | 2023-01-26 | 2023-02-22 | 2023-05-01
|  | Credit Support | Update
|  | Acceptable Credit Criteria | Update
WEM Procedure: Exempting Nonconforming Indeterminate Systems | 2.28.21 | Information required from Intermittent Loads | New | M |  | 2023-01-26 | 2023-02-22 | 2023-05-01
Performance of intertripping protection schemes assessment criteria
Performance standards for treatment of Intermittent Loads
WEM Procedure: Data and IT Interface Requirements | 2.36.5 | Cyber | New | S | 2020-12-17 | Complete | Closed - 16/07/2021 | Complete | 2021-07-29
Portal and IDAM
WEM Procedure: Indicative Facility Class and RCM Facility Class Assessment (First Revision) | 4.8A.7 | Indicative Facility Class Registration | New | L | 2021-05-27 | Complete | Closed - 09/07/2021 | Complete | 2021-07-29
WEM Procedure: Indicative Facility Class and RCM Facility Class Assessment (Second Revision) | 4.8A.7 | Indicative Facility Class Registration | New | L | 2021-10-28 | Complete | Closed - 08/11/2021 | Complete | 2021-12-01
WEM Procedure: Indicative Facility Class and RCM Facility Class Assessment (Third Revision) | 4.8A.7 | Indicative Facility Class Registration | New | L | 2022-01-27 | Complete | Closed - 19/01/2022 | Complete | 2022-03-01
WEM Procedure: Transitional Registration | 1.47.12 | Assignment of a Facility Class | New | S |  | 2022-12-08 | 2023-01-17 | 2023-03-23
Mapping of existing Facilitites to new Facility Classes
WEM Procedure: Monitoring and Reporting Protocol | 2.15.4 | Monitoring and reporting compliance | Update | M |  | 2023-06-29 | 2023-07-25 | 2023-10-01
WEM Procedure: System Restart | 3.7.40 | System Restart Standard and System Restart Plan Methodology and process | New | M | 2022-04-24 | Complete | Closed - 28/04/2022 | Complete | 2022-06-01
Changes from the standard form contract
Procurement of System Restart Services
System Restart Standard Review