## Title Page
Procurement Risk Workbook
Title:
[Insert Contract Title Here]
Reference Number:
[Insert the Reference Number]
State Agency:
[Insert State Agency Name]
Government of Western Australia
Department of [insert State Agency name]

## Risk Assessment Details
Risk Assessment Details
INSTRUCTIONS : For the procurement risk assessment process to be effective, it is important for the right people to be involved. Complete the tables below to identify stakeholders for the risk assessment process. It is recommended that you review and update this form as required during the procurement planning and contract management stage of the procurement. Save a PDF copy of this worksheet each time it is updated and at each contract milestone or approval stage to keep a record of the risk assessment process at that point in time.
Risk Assessment Details Completed By : | [Insert name & title] | Date of last update : [Insert]
Contract Details
Procurement Type : | [goods / services / works]
Contract Number & Title : | [Insert number and title]
Contract Type : | [Insert type of contract, e.g.: period contract, one-off purchase, supply and install, with maintenance, standing offer (CUA or agency panel), etc.]
Contract Description : | [Insert description of goods / services / works to be procured. Delete if the Contract Title adequately describes the deliverables.]
State Agency : | [Insert State Agency name]
State Agency Contract Manager’s Name : | [Insert name & title]
Department of Finance Facilitator's Name (if applicable) : | [Insert name & title]
Risk Assessment Participants
NAME | TITLE | ROLE
[Insert name] | [Insert title] | [Insert role, e.g. facilitator, expert, State Agency representative, Department of Finance representative]

## Risk Register
Risk Register
INSTRUCTIONS :
This risk register table should be completed using your agency's internal risk guidance to determine the likelihood and consequence ratings.
The risk assessment process needs to consider both procurement process related risks and goods, services and/or works related risks. The risk register should be reviewed an updated (as required) during both the procurement planning and contract management stage of a procurement. The review frequency will depend on the nature of the procurement, for example a risk register for a works project should be a live management document rather than a static "point in time" record. It is recommended that you save a PDF copy of this worksheet at each contract milestone or approval stage to keep a record of the risk assessment process at that point in time.
Refer to the Risk Management in the Procurement Context Guideline for more information, including a description of the terms and concepts used in this template. The 'Examples of Risks' worksheet in this workbook can also be used to brainstorm risks and treatment strategies that may be applicable.
Contract Number & Title : |  |  |  |  | State Agency :
Risk Manager : |  | [Insert name & title] |  |  | Last Updated :
Risk register table
Activity / Event / Process / Deliverable | Risk Reference | Critical Success Factors | Risk | Causes | Controls | Consequences | Risk level | Maximum Possible Loss | Maximum Probable Loss | Action(s) | Residual Risk | Type of Insurance
Briefly describe the activity, event, process, or contract deliverable that is the source of the risk. | A number to identify the risk to assist with discussions. | What needs to go right? | What can go wrong? | What could potentially cause that to happen? | Existing mechanisms in place that prevent or mitigate the event occurring or limit its impact. | What are the potential results? | Refer to your State Agency’s risk ref tables & take existing controls into account. | AU$ estimate of costs / damages that could be incurred – without controls or treatments in place. | AU$ estimate of costs / damages that could be incurred – with controls or treatments in place. | What action(s) if any will you take to treat the risk? Who is responsible and when should this occur? (In addition to existing controls) | Predicted level of risk after action(s). | e.g. PL, PI, W/C, Prod, or Not Applicable.
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :
[7 empty] | Likelihood : |  |  |  | Likelihood :
[7 empty] | Consequence : |  |  |  | Consequence :
[7 empty] | Level of Risk : |  |  |  | Level of Risk :

## Risk Identification Form
Risk Identification Form
INSTRUCTIONS : This template can be used to explore an individual risk in detail. Refer to the Risk Management in the Procurement Context Guideline for more information, including a description of the terms and concepts used in this template. It is recommended that you review and update this form as required during the procurement planning and contract management stage of the procurement. Save a PDF copy of this worksheet each time it is updated and at each contract milestone or approval stage to keep a record of the risk assessment process at that point in time.
Form Completed By : (Name and Title) |  |  | Date :
Contract Number & Title :
Procurement Type : (Goods / Services / Works)
Risk Ref No. : | [make risk reference numbers indicative of the category of risk e.g. Procurement Planning Risk 1 = PPR1, Service Delivery Risk 1 = SDR1]
Activity / Event / Process / Deliverable :
Critical Success Factors : (What needs to go right?)
Risk : (What can go wrong?)
Causes : (What could cause that to happen?)
Controls : (Existing preventative or mitigative measures)
Consequence(s) if risk occurs : (Outcome or impact of the risk occurring)
Likelihood Rating : |  | Consequence Rating : | Level of risk :
ACTIONS (What can you do about it?)
|  | Due Date : | Status : (In progress/completed)
|  | Due Date : | Status : (In progress/completed)
|  | Due Date : | Status : (In progress/completed)
|  | Due Date : | Status : (In progress/completed)
CONSEQUENCE, LIKELIHOOD & LEVEL OF RISK AFTER ACTIONS
Likelihood Rating : |  | Consequence Rating : | Level of risk :
Maximum Probable Loss ($) : (Worst / largest $ impact after risk treatment)

## Examples of Risks
Examples of Risks and Treatment Actions
INSTRUCTIONS : Use these examples to identify potential risks for completing the detailed risk assessment process. The examples are generic and are not intended to capture all possible scenarios. The examples are provided for guidance only and should be adapted to fit the specifics of your procurement and overall project. Seek advice from procurement or risk subject matter experts within your agency or externally, as required.
1. Context - Procurement Risk Management
PLANNING, PREPARATION, PROCESSES
| Some of the risks that might be encountered are: |  | Some of the treatment actions that could be implemented are:
● | State Agency does not have legal capacity or delegated authority to procure. | ● | Check that the contract is consistent with the organisation’s business objectives.
● | No allowance made for whole of life (life cycle) costs. | ● | Evaluate alternative delivery and procurement methods.
● | Proper contracting processes are not followed. | ● | Conduct feasibility study including market analysis and revenue estimates.
● | Supplier selection processes don’t achieve value for money or equity. | ● | Check legal capacity of State Agency to undertake the contract.
● | Wrong procurement method used. | ● | Confirm sources of funds including ongoing obligations arising from the contract.
● | Conflict with existing contracts. | ● | Produce cash flow estimates and monitor expenditure against estimates.
● | Delays in obtaining approvals. | ● | Clearly define the roles and responsibilities of team members.
● | Contract deliverables don’t meet expectations. | ● | Define the objectives and expected outcomes of the contracting project.
● | Government policies not followed. | ● | Check the scope against the allocated budget.
● | Inappropriate financing arrangements adopted. | ● | Ensure adequate time is allowed for evaluation, testing and installation.
● | Lack of information or experience in procuring a unique or unconventional good/service/works means the specification or selection criteria are inadequately drafted. | ● | Confirm that operational budgets have been considered and provided for.
|  | ● | Identify, agree and document the procurement process.
|  | ● | Ensure that processes are documented and contracting officers trained.
|  | ● | Ensure the proposed tendering process is ethical and delivers value for money.
|  | ● | Check the proposed method of procurement against time / cost budgets.
|  | ● | Release a draft Request to industry for comment.
|  | ● | Check whether any relevant existing whole of government contracts exist or if your State Agency already has a contract in place for the goods, services or works.
|  | ● | Document the approvals required and give advanced notice to those giving the approvals.
|  | ● | Identify zoning, planning or licensing issues that may affect the project.
|  | ● | Ensure scope is defined, documented ang understood.
|  | ● | Obtain an independent opinion on the clarity of the scope.
|  | ● | Ensure adequate technical knowledge is used in scope definition.
|  | ● | Use a standard brief where possible.
|  | ● | Identify government policies that apply to this contract and ensure compliance.
INDUSTRY
| Some of the risks that might be encountered are: |  | Some of the treatment actions that could be implemented are:
● | Lack of interest by suppliers in tendering on the project. | ● | Review the levels of market competitiveness and adopt an appropriate procurement method.
● | Undue interference by the industry in the way the contract is let. | ● | Inform industry as far in advance as possible, and consider conducting an industry briefing if appropriate.
● | Contract takes too much work away from small businesses. | ● | Identify most effective means of communicating the contract opportunity to industry.
● | There is no established industry capable of carrying out the work. | ● | Advertise the contract in the most appropriate media.
● | Project promoted towards the wrong industry. | ● | Review quality assurance requirements and compare with industry capacity.
● | Inability of the industry to resource the contract. | ● | Consult with industry groups.
● | Lack of capacity of individual contractors. | ● | Review the likely impact of the contract on existing businesses.
● | Overheated market conditions at tender time. | ● | Ensure that the size of the contract is compatible with the size of the industry.
● | Perceptions of bias towards certain suppliers. | ● | Ensure that a competitive industry exists that is capable of undertaking the project.
|  | ● | Identify and survey sources of independent industry knowledge.
|  | ● | Check company structure and financial capability of preferred Respondent(s) prior to awarding contract.
|  | ● | Check prior performance of suppliers.
|  | ● | Request a tender response in sufficient detail to enable assessment.
|  | ● | Assess preferred Respondents’ history of staff turnover and industrial relations performance.
|  | ● | Check supply lines including proposed subcontractors.
|  | ● | Request and check references from Respondents.
|  | ● | Consider need for shortlisting as part of the selection process.
|  | ● | Use appropriate benchmarks for qualitative aspects of selection process, e.g. industry awards.
|  | ● | Consider using proposed methodology as one of the selection criteria.
|  | ● | Define selection criteria, weighting and assessment method prior to tender.
|  | ● | Ensure contractor selection process is transparent.
STAKEHOLDERS
| Some of the risks that might be encountered are: |  | Some of the treatment actions that could be implemented are:
● | Non-compliance with policies. | ● | Develop a communication plan for stakeholders.
● | Resistance by community interest and pressure groups. | ● | Identify government policies (e.g. Aboriginal Procurement Policy participation requirements, Priority Start, etc.) that apply to the contract and ensure compliance.
● | Resistance by minority groups. | ● | Consider local content issues.
● | Adverse media interest. | ● | Identify issues that may be sensitive or confidential.
● | Resistance or opposition by other agencies. | ● | Determine community awareness and interest in the contract.
● | Conflict between different stakeholders. | ● | Identify likely interest and lobby groups (including local).
|  | ● | Keep public relations branch informed on high-risk contracts.
|  | ● | Identify potential conflicts between stakeholders.
|  | ● | Keep relevant stakeholders briefed.
PROJECT MANAGEMENT
| Some of the risks that might be encountered are: |  | Some of the treatment actions that could be implemented are:
● | Procurement project lacks direction and control. | ● | Define and document roles and responsibilities of all parties involved in the contract.
● | Contract is poorly managed. | ● | Develop and measure progress.
● | Inexperienced or incapable team appointed. | ● | Determine appropriate level of contract administration and management.
● | Instructions not correctly conveyed to team members. | ● | Develop a contract management plan.
|  | ● | Identify and develop appropriate contract reporting requirements.
|  | ● | Identify appropriate staging of payments.
|  | ● | Ensure contract managers understand the process requirements and responsibilities in the contract manager’s role.
CONTRACT
| Some of the risks that might be encountered are: |  | Some of the treatment actions that could be implemented are:
● | Breach by the contractor. | ● | Identify correct contract type for the type of work required.
● | Breach by the contract authority or customer. | ● | Use standard form of contract where applicable.
● | Inability to enforce performance. | ● | Obtain legal advice when non-standard contract or supplier’s contract is used.
● | Inability to terminate the contract. | ● | Ensure that the appropriate type of specification (e.g. performance, functional, technical) is used.
● | Payment is made for goods, services or works that aren’t delivered. | ● | Define and document required service levels.
● | Goods, services or works delivered are not as expected. | ● | Develop a contract management plan that includes monitoring and management of contractual obligations of all parties.
● | Contractor unable to fund repairs to damaged work or claims for damages or injury. | ● | Develop contract Key Performance Indicators and monitor and review.
|  | ● | Ensure documents are concise, precise and unambiguous.
|  | ● | Use appropriate method of formalising contract acceptance
|  | ● | Ensure contract documents reflect project management requirements.
|  | ● | Confirm contractor payment arrangements and responsibilities.
|  | ● | Check the adequacy of retention, security and insurance.
|  | ● | Ensure that proposed payment schedules are consistent with the value of work received from the contractor.
|  | ● | Develop a partnering or alliance relationship with the contractor.
|  | ● | Assess the appropriate level of security and insurances required to protect the customer and ensure that the contractor provides them.
2. Context - Goods, Services or Works Risk Management
NATURE OF THE GOODS, SERVICES OR WORKS
| Some of the risks that might be encountered are: |  | Some of the treatment actions that could be implemented are:
● | Contract doesn’t deliver the expected benefits. | ● | Check the adequacy of time and cost targets, obtain approval to adjust if necessary and confirm the targets early in the project.
● | Unachievable time and cost targets set. | ● | Conduct regular reviews of the targets.
● | Contract deliverables don’t meet expectations. | ● | Obtain input from an appropriate expert as to whether the deliverables are realistic and achievable.
● | Difficulty developing the goods, services or works. | ● | Identify aspects of the project that are unique and either validate their need or standardise.
● | Difficulty coordinating the goods, services or works. | ● | Select a contracting team with appropriate experience.
● | Difficulty building/developing the goods, services or works. | ● | Carry out product testing.
● | Difficulty integrating the goods, services or works into existing environment. | ● | Identify overseas components, their availability and criticality to the project and consider pre-purchase if appropriate
● | Difficulty or delay in transition from incumbent supplier to potential new supplier | ● | Identify hazardous materials or practices being used to develop or deliver the goods, services or works and ensure that appropriate handling procedures are used.
● | Difficulty or delay in obtaining overseas components. | ● | Identify new technologies being used, determine risks involved and develop testing and installation procedures and contingency plans if necessary.
● | Unsafe use of hazardous materials or practices. | ● | Ensure that the project allows for improved technologies to be incorporated at a later date.
● | Failure of new technologies used in the goods, services or works. | ● | Include a delivery, test and installation phase in the project program.
● | Technologies used in the goods, services or works becomes obsolete. | ● | Describe the goods, services or works in a tangible and unambiguous way.
● | Delays in delivering, testing and installing the goods, services or works. | ● | Ask suppliers to explain their understanding of the contract requirements and deliverables.
● | Final goods, services or works doesn’t meet expectations or produce desired outcomes. | ● | Consider whether the contract should have provisions for payments to be withheld if goods, services or works is not satisfactory.
DELIVERY ENVIRONMENT
| Some of the risks that might be encountered are: |  | Some of the treatment actions that could be implemented are:
● | Difficulty delivering the goods, services or works. | ● | Identify regional issues that may affect the delivery of the goods, services or works such as seasonal weather patterns, remoteness, accessibility, availability of resources, services, etc. and develop management plans.
● | Restrictions due to the nature of the precinct and surrounds. | ● | Ensure time-frames and cost budgets account for regional issues.
● | Restrictions due to the special needs of the users or occupiers. | ● | Conduct an environmental impact assessment.
● | Unavailability of required services and resources. | ● | Request details of how the supplier plans to carry out the work.
● | Injury or hazards caused by materials present or activities undertaken. | ● | Identify services that may be required to deliver the contract and ensure they are available.
● | Delays or damage due to natural events. | ● | Identify hazardous materials and activities on the site and develop management plans.
● | Restrictions or delays due to planning and zoning requirements. | ● | Ensure the supplier is aware of obligations.
● | Unforeseen or unplanned fluctuations in foreign exchange rates. | ● | Ensure that the supplier insurance requirements are compatible with the hazards or problems that might be encountered.
● | Goods, services or works has adverse impact on the natural environment. | ● | Identify what services are required and ensure they are available.
|  | ● | Identify zoning, planning or licensing issues that may affect the project.
|  | ● | Check and confirm financial arrangements.
|  | ● | Consider strategies to minimise the impact of foreign exchange movements
|  | ● | Identify and respond to environmental issues such as materials, technology, energy, and recycling.
|  | ● | Customise specification to take into account environmental factors.
INDUSTRY
| Some of the risks that might be encountered are: |  | Some of the treatment actions that could be implemented are:
● | Failure of contractor(s). | ● | Check that the budgets take into account the predicted market situation.
● | Poor performance of contractor(s). | ● | Ensure that the contract makes the contractor responsible for industrial action.
● | Overheated market during the project delivery. | ● | Consider pre-purchasing material that is likely to be in short supply when required.
● | Industrial unrest.
● | Material unavailability.
STAKEHOLDERS
| Some of the risks that might be encountered are: |  | Some of the treatment actions that could be implemented are:
● | Change in Government policies. | ● | Develop a communication plan for stakeholders
● | Resistance by community interest and pressure groups. | ● | Identify issues that may be sensitive or confidential.
● | Adverse media interest. | ● | Determine community awareness and interest in the contract.
● | Resistance or opposition by other agencies. | ● | Identify likely interest and lobby groups (including local).
● | Conflict between different stakeholders | ● | Keep public relations branch informed on high-risk contracts.
|  | ● | Identify potential conflicts between stakeholders.
|  | ● | Keep relevant stakeholders briefed.
PROJECT MANAGEMENT
| Some of the risks that might be encountered are: |  | Some of the treatment actions that could be implemented are:
● | Vital tasks missed or poorly carried out by project team. | ● | Adopt an appropriate project management structure
● | Instructions not correctly conveyed to team members. | ● | Adopt appropriate project control structure
● | Conflict between team members. | ● | Develop appropriate team communication
● | Inter-agency relationships on joint projects function poorly. | ● | Develop project plan (at appropriate level of detail)
|  | ● | Ensure appropriate resources allocated
|  | ● | Ensure project plan and progress is documented
|  | ● | Consider using an experienced project manager
|  | ● | Review approach used on previous/similar projects