# Australian Centre for Child Protection - WA Child Protection Project

Final close out report - August 2023

In 2021 the Department of Communities (Communities) commissioned the Australian Centre for Child Protection (ACCP) to undertake research to inform and assist Communities in the development of a Western Australia (WA) child protection reform roadmap and implementation plan (the report).

The ACCP commenced the project on 4 June 2021 in partnership with PwC Indigenous Services, which ensured the work was grounded with a strong cultural perspective.

The ACCP project team reviewed and analysed over 100 documents and reports, conducted targeted internal consultations and overlayed their work with expertise and learnings from child protection research and projects undertaken by Professor Leah Bromfield at the ACCP.

The ACCP report was designed to guide internal project setting; future reform; and strategy development.

The work undertaken by the ACCP highlighted three areas that Communities could focus on:

- Adoption of a robust Implementation Framework for Child Protection Reform that has a clear governance structure including Aboriginal cultural governance and principles of practice

- Development of a child protection system with strong stakeholder engagement, workforce capability, a whole-of-system outcomes framework, access to timely and accurate data, a risk management framework and capacity to respond in an agile manner

- Ensuring the out of home care Commissioning Plans align with the development and implementation of the 10-year Roadmap to Reduce the Number of Aboriginal Children in Care (the Roadmap).

Implementation

This the final acquittal report that provides detailed information to highlight the significant change and work undertaken since 2021.

Since the ACCP WA report the development of a systematic approach to prioritisation of child protection reform initiatives, in line with the principles of project portfolio management, is underway. Project-level governance has been reinforced and communicated via a project management framework and defined project management practices, commensurate with the size and complexity of the project or program; and engagement with stakeholders recognising the importance of co-design and working in partnership with Aboriginal people, Aboriginal communities and Aboriginal organisations is paramount and embedded throughout both project and strategy implementation lifecycles.

Safe and Supported: the National Framework for Protecting Australia’s Children 2021-2031 (Safe and Supported) is driving the child protection reform agenda and the prioritisation of action to improve the lives of children, young people and families experiencing disadvantage or who are vulnerable to abuse and neglect. Safe and Supported is being implemented through two five year Action Plans, including an Aboriginal and Torres Strait Islander plan, that outline real measurable actions to support improved outcomes for children and families at risk.

Keeping Aboriginal children safe with their families is fundamental to maintaining their sense of identity and connection to Country and culture. Communities has partnered with SNAICC – National Voice for our Children, to develop the 10 Year Roadmap to Reduce the Number of Aboriginal Children in Care (Roadmap). The Roadmap will outline how the WA Government will address Target 12 of the National Agreement on Closing the Gap (by 2031, reduce the rate of over-representation of Aboriginal and Torres Strait Islander children in out of home care by 45 per cent) and Western Australia’s responses to ‘Safe and Supported: the National Framework for Protecting Australia’s Children 2021-2031’.

In March 2023, SNAICC held a Roadmap Co-Design Forum. Aboriginal representatives attending the forum heard the feedback from the regional consultations and worked together to develop recommendations for the Roadmap. SNAICC is scheduled to deliver the draft Roadmap, first Action Plan and a proposed governance mechanism to guide implementation in mid 2023. The ACCP report has informed the development of the Roadmap and Communities’ commissioning work.

The summary below outlines how this work has been used by Communities to inform reform projects.

| No. | Action and link to ACCP Recommendations | Initiatives that will address key action | Comments |
| --- | --- | --- | --- |
| Theme Area 1: General systems and specific strategy actions – priority one |  |  |  |
| Key Action 1 | Engage internal stakeholders in the process of System Implementation and ongoing Strategy Reform of Communities | Communities Project Management templates and processes | August 2023 Status – Completed Stakeholder analysis and engagement is clearly prioritised and integrated in Communities’ Project Management processes throughout the project lifecycle. Stakeholder identification and analysis occurs in the ‘Initiate’ and ‘Planning’ phases of project/program scoping and ongoing feedback and engagement is facilitated throughout project/program ‘Delivery’ and ‘Close-out’ phases. Engagement strategy/method/frequency is informed by IAP2’s Public Participation Spectrum. September 2022 Communities will continue to engage internal stakeholders in the process of implementing pilot and reform projects and development of strategy including internal regional stakeholders. For example - Webinars or practice clinics were held on out of home care commissioning and legislative amendments in 2021-2022. The engagement of internal stakeholders will also be included within the governance structure (see below) |
| Key Action 2 | Install Implementation Governance Structure including embedded Cultural Governance | Communities Project Management templates and processes | August 2023 Status - Completed Communities’ Project Management approach ensures project governance is established and maintained throughout the project/program lifecycle, commensurate with the size and complexity of the project/program. This is supported by robust project documentation, Terms of Reference for project governance bodies and embedding cultural considerations that align with the Aboriginal Empowerment Strategy WA 2021-2029 in every project plan. September 2022 Communities will continue to develop project management plans for all projects, the plans will include information about proposed governance and include cultural engagement and governance. A robust Implementation Framework for child protection reform projects will be developed with clear governance and engagement with internal and external stakeholders as appropriate. |
| Key Action 3 | Assign Strategy Leads for each initiative | Communities Project Management templates and processes | August 2023 Status - Completed Strategy-level initiatives have been allocated and are being led by the appropriate portfolio area. Communities will continue to refine the approach to managing cross-portfolio initiatives, including consideration of a whole-of-Department Project Portfolio Management framework. September 2022 Communities will continue to develop project management plans for all projects, the plans will include information about proposed engagement and leads for the project and implementation. A robust Implementation Framework for child protection reform projects will be developed with clear governance and engagement with internal and external stakeholders as appropriate. |
| Key Action 4 | Consider alternative options to the total re-commissioning of OOHC at this time | Communities Commissioning Plan | August 2023 Status – Completed Communities considered the recommendation to assess alternative options to the total re-commissioning of OOHC. Communities’ current strategic direction, informed by the commitment to the National Agreement on Closing the Gap, the Aboriginal Empowerment Strategy, ACCO Strategy and Safe and Supported, reiterates the importance of progressing the commissioning process for the out of home care sector. The re-commissioning process is continuing and has progressed to negotiation, transition and implementation of the new service models. September 2022 Communities considered all options, based on the number of extensions already provided to services and the extensive co-design work previously undertaken it was determined to proceed with commissioning work at this time. It is noted that each of the four streams currently being commissioned have different procurement approaches and timelines, this mitigates the risk of one organisation needing to participate in multiple tender processes at any one time. Communities continues to provide support to the out of home care sector and ACCOs to participate in the commissioning process including opportunities to provide direct feedback to service specifications and procurement approaches. Engagement and communication with the out of home care sector has been regular and ongoing, with opportunities provided for discussion, questions and information sharing. |
| Key Action 5 | Develop OOHC re-commissioning plan with clear timeline, project team and alignment with strategy elements | Communities Commissioning Plan | August 2023 Status – Completed OOHC commissioning process has now progressed to negotiation, transition and implementation of the new service models. September 2022 Communities has developed an out of home care commissioning plan that includes clear timeframes which has been communicated to the sector since mid-2021. Regular updates are provided to sector on the progress of this work, and the Commissioning website is regularly updated to ensure all information is easily accessible to current and future service providers. The Request for Tender for out of home care Services was released mid-June 2022 on Tenders WA. The tender was open for 8 weeks and closed on 11 August 2022. The Request for Tender represents the strengthening of our OOHC system and supporting better outcomes for children and young people in care. The future out of home care system will deliver a suite of care arrangements that provide different levels of support to children with different and changing needs. |
| Key Action 6 | Conduct a risk assessment (and treatment) for the OOHC procurement process and its capacity to fulfil the OOHC strategy reform | Communities Commissioning Plan | August 2023 Status – Completed The OOHC reform project risk assessment was developed by the Commissioning Project Management Office within the Business and Operational Support Services Division. This includes all aspects of the contract negotiations and implementation of the reform. September 2022 The commissioning work is based on extensive sector engagement and consultation over the last eight years – including the establishment of a cross-sector Independent Reference Group and resulting report ‘Care and Protection System Co-Design Report. This work has continued to inform each stage of the commissioning work including refinement of service types and the development of service level outcomes and evaluation framework. The risks associated with all four commissioning streams have been presented to Communities Leadership Team The commissioning process is the first stage of broader OOHC reforms that will occur. |
| Key Action 7 | Establish a targeted ACCO capacity building and engagement strategy to facilitate the OOHC procurement and service design process for 2022 | Communities Commissioning Plan Communities ACCO Strategy 2022-2032 | August 2023 Status – Completed The Aboriginal Community Controlled Organisation (ACCO) Strategy 2022 to 2032 is directly aligned to Priority Reform Two of the National Agreement on Closing the Gap, “Building the Community-Controlled Sector” and Outcome Eight, “Strong economic participation and development of people and their communities”, and the Aboriginal Empowerment Strategy 2021-2029. The ACCO Strategy remains focused on delivering the key actions detailed in Implementation Plan One. In July 2022, Communities provided small capability building grants to 13 ACCOs to develop their knowledge and skills to participate competitively in tendering for Out of Home Care services. Communities are committed to funding future ACCO Capability Building Grants Programs to support the growth of the community-controlled sector. September 2022 A key priority of the commissioning of out of home care services is to increase the number of ACCO’s delivering out of home care services. To support this work, an EOI was released in early 2022 to seek interest from ACCOs in delivering out of home care services. 44 ACCO’s registered their interest, with representation from each region of WA. A follow up webinar was held on 3 March 2022 to provide information on the care types and proposed procurement approach. Following this, one on one meetings have been held with each ACCO to understand any barriers to them participating in the procurement process. Aboriginal Outcomes is supporting ACCOs with identifying any support that Communities can provide to assist their participation in the process. Through this engagement, it is evident ACCO’s have already undertaken consultation within their organisations and communities about the local, placed-based needs of their children and young people, which will inform the proposed service model. Communities is also progressing with a direct procurement approach for ACCOs. Non ACCO’s will be required to respond to an open tender. Communities has provided a grant to Yorganop to develop a transition plan for Aboriginal children in care and also offered their assistance to new ACCOs entering the out of home care space by sharing their experiences and considerations as the only current ACCO delivering out of home care services. The ACCO Strategy seeks to improve Communities’ commissioning and delivery of services to Aboriginal children, families and communities, and to support ACCOs to increase their capacity to deliver place-based, culturally appropriate services across WA. The ACCO Strategy aligns directly to a number of Priority Reform Areas and Socio-Economic targets identified within the National Agreement on Closing the Gap and will assist Communities in meeting its commitment as a signatory to the Agreement. Communities is the lead agency for the Early Childhood Care and Development Sector Strengthening Plan and the ACCO Strategy will identify, build capability and develop opportunities for ACCOs to provide services to Aboriginal people across these areas. The ACCO Strategy focuses on three key pillars; cultural safety and governance, respectful partnerships and economic opportunities. |
| Key Action 8 | Establish clear stakeholder engagement strategy including co-design model | Communities Commissioning Plan Communities Partnership Framework | August 2023 Status – Completed OOHC commissioning process has now progressed to negotiation, transition and implementation of the new service models. September 2022 Communities has developed an out of home care commissioning plan that includes clear timeframes this has been communicated to the sector since mid-2021. Regular updates are provided to sector on the progress of this work, and the Commissioning website is regularly updated to ensure all information is easily accessible to current and future service providers. Communities has developed and adheres to the Communities Partnership Framework Communities has also committed to the Aboriginal Empowerment Strategy. |
| Key Action 9 | Review the Project Plan for the development of the 10-Year Roadmap given the impacts of the OOHC re-commissioning | Communities Commissioning Plan 10 Year Roadmap to Reduce the Number of Aboriginal Children in Care | August 2023 Status – Completed SNAICC has been contracted under a Grant Agreement to develop a 10 Year Roadmap. SNAICC conducted a series of community forums in which Aboriginal communities came together to provide input toward the development of the Roadmap In March 2023, SNAICC held a central state-wide design forum bringing together Aboriginal community representatives from across WA, and government representatives from a range of agencies. SNAICC is due to finalise the roadmap, first action plan and proposed Government mechanism for implementation of the roadmap by mid-July. Over the past 12 months, Secretariat of National Aboriginal and Islander Child Care (SNAICC) have undertaken a Statewide engagement process to ensure that the voices of Aboriginal communities and organisations are front and centre in development of the 10-year Roadmap to reduce the number of Aboriginal children in care (the Roadmap). To support the engagement, SNAICC partnered with local Aboriginal Community Controlled Organisations with knowledge of the diverse WA Aboriginal community, child protection history, policy and practice to conduct culturally safe consultation forums across the State. In addition, SNAICC have held interviews and meetings with a number of key stakeholders, including Communities’ frontline child protection practitioners and Aboriginal staff. SNAICC held a two-day central design forum on 21-22 March 2023, bringing together Aboriginal community representatives from across WA, and Government representatives from the Departments of Communities, Premier and Cabinet, Health, Justice and Education, along with the WA Police Force and the Mental Health Commission. The co-design forum built on what was heard at community forums and feedback from other key stakeholders. Communities and SNAICC are continuing to work with Government agency partners on the Roadmap to ensure commitment to, and authorisation of, assigned actions. The 10-year Roadmap to Reduce the Number of Aboriginal Children in Care Between October 2022 – February 2023 SNAICC partnered with Aboriginal Community Controlled Organisations in Western Australia to hold consultations with Aboriginal community. Roadmap consultations were held in Perth, Bunbury, Kununurra, Broome, Geraldton, Carnarvon, Roebourne, Port Hedland, Newman and the Central Desert/the Lands. SNAICC have also consulted with Communities’ staff and other key WA stakeholders. Communities has engaged Communities’ staff and key government partner agencies in the Roadmap project including Departments of Education, Health, Justice and Premier and Cabinet, Western Australia (WA) Police, and Mental Health Commission. In March 2023, SNAICC held a Roadmap Co-Design Forum. Aboriginal representatives attending the forum heard the feedback from the regional consultations and worked together to develop recommendations for the Roadmap. SNAICC is scheduled to deliver a draft Roadmap, first Action Plan and a proposed governance mechanism to guide implementation by 31 July 2023, for WA Government consideration. September 2022 Communities decided to conduct the two projects during 2021/22 Clear communication protocols will be established to ensure any learnings from either project can be shared and updated as required. The Executive Director of the SCPU will oversight and lead both projects to ensure that all synergies are maximised. Communities has partnered with Secretariat of National Aboriginal and Islander Child Care (SNAICC) – National Voice for our Children through a grant agreement to develop a Roadmap and first Action Plan, which will provide a long-term vision to address the over-representation of Aboriginal children in care with a focus on culturally responsive, effective and sustainable solutions. The Roadmap will outline how the State Government will address Target 12 of the National Agreement on Closing the Gap and Western Australia’s (WA) responses to Safe and Supported: the National Framework for Protecting Australia’s Children 2021-2031. Hearing the voices of Aboriginal children and their families will be central to the Roadmap’s development later this year. SNAICC will subcontract local Aboriginal Community Controlled Organisations with knowledge of the diverse WA Aboriginal community, child protection history, policy and practice to conduct culturally safe state-wide consultation forums across WA. The solutions will be identified by Aboriginal people and communities, in partnership with the Department, other government agencies and sector partners through governance groups established to provide input into and oversee development of the Roadmap and Action Plan. The Roadmap will build on the reforms, initiatives and pilots already underway and which are having an impact, and propose ways to embed cultural changes and new ways of working by Communities and across Government. The Roadmap is due for completion in mid-2023. |
| Theme Area 2: General systems and specific strategy actions – priority two |  |  |  |
| Key Action 10 | Endorse whole of System Reform Strategy with clear program logic | Communities Project Management templates and processes | August 2023 Status - Completed The Specialist Child Protection Unit established the SCPU Project Management Office in October 2022. A project management framework has been rolled out and a reporting dashboard for tracking existing projects/programs that are contributing to child protection reform has been implemented. Communities will continue to refine the approach to managing child protection reform initiatives. September 2022 Communities will continue to develop project management plans and processes to capture child protection reform projects. A robust Implementation Framework for child protection reform projects will be developed with clear governance and engagement with internal and external stakeholders as appropriate. This work will be coordinated by the SCPU team and will also consider Communities commitments under Closing the Gap. |
| Key Action 11 | Develop whole of System Outcomes Framework | Communities Outcomes Framework | August 2023 Status - Completed Safe and Supported: the National Framework for Protecting Australia’s Children 2021-2031 (Safe and Supported) is informing the prioritisation of efforts to reduce child abuse and neglect and its intergenerational impacts. Safe and Supported is underpinned by a Theory of Change and two targeted Outcomes Frameworks, developed in partnership with SNAICC and the Aboriginal and Torres Strait Islander Leadership Group. The National Coalition on Child Safety and Wellbeing was also consulted. The Outcomes Frameworks and Theory of Change align with the Aboriginal and Torres Strait Islander Child Placement Principle and the National Agreement on Closing the Gap to ensure all child protection reform work is aligned to achieve the same outcomes and realise the intended impact. September 2022 Communities will continue to develop project management plans and processes including outlining how projects deliver on the Communities outcomes framework. A robust Implementation Framework for child protection reform projects will be developed with clear governance and engagement with internal and external stakeholders as appropriate. |
| Key Action 12 | Review previous and/or develop a new Aboriginal Practice Framework | Supported | August 2023 Status - Completed The Aboriginal Cultural Framework has been developed, supported by Aboriginal Cultural Learning Strategy. The Aboriginal Cultural Capability Reform Program (ACCRP) is driving an agency-wide cultural reform agenda aimed at improving the cultural capability of the Department of Communities (Communities). Initial state-wide engagement with internal and external Aboriginal stakeholders has been completed in partnership with Aboriginal business, Kambarang Services, to inform the development of the draft Aboriginal Cultural Framework (the Framework) and draft Aboriginal Cultural Learning Strategy (Learning Strategy). The Framework and Learning Strategy will ensure Communities meets Priority Reform Area Three of the National Agreement on Closing the Gap, Transforming Government Organisations, and will operationalise how Communities will build, embed and maintain a culturally competent workforce and develop culturally capable systems, policies and practices that will enable better outcomes for Aboriginal people and communities. September 2022 The review and refresh of the Framework to be considered. |
| Key Action 13 | Review current data systems and develop a fit-for-purpose data system for use across Communities | A business case is being developed to seek Office of Digital Government funding for the replacement of the ageing Child Protection System known as Assist. | August 2023 Status – In progress Communities is developing the business case for a replacement to the current Child Protection System (Assist). A request for information will be issued to the market shortly. The outcome of this will inform the business case. September 2022 Internal funding has been allocated to develop a business case to support a full bid to the Office of Digital Government - Digital Capability Fund for a replacement to the current Child Protection System (Assist). The current system is over ten years old and is limited in the provision of statistical data and report extraction. As part of the development of the requirements for a new system, agency wide consultation will occur together with a thorough review of existing data availability to identify the full data and client/child information requirements for the new System. |
| Key Action 14 | Review the workforce readiness to complete the current and future reform strategies and apply any remedial treatment | SCPU Workplan | August 2023 Status – Ongoing Safe and Supported: the National Framework for Protecting Australia’s Children 2021-2031 (Safe and Supported) is informing the prioritisation of efforts to reduce child abuse and neglect and its intergenerational impacts. Communities’ commitments under Safe and Supported are directing efforts to ensure the future sustainability of the child protection workforce. This will include attraction and retention, capacity and capability approaches, embedding trauma-informed and culturally aware services and peer support through the delivery of specific projects, including: - WA Signs of Safety Project - One Communities Family and Domestic Violence Informed Practice Approach Communities’ People division has commenced work to develop a whole of Communities Workforce Planning Framework and Communities Capability Framework. This will underpin further targeted workforce strategies. September 2022 A robust Implementation Framework for child protection reform projects will be developed with clear governance and engagement with internal and external stakeholders as appropriate. SCPU to consider and establish a small project management team to coordinate and support child protection reform work across Communities. |
| Key Action 15 | Develop a 5 Year Cultural Capacity Building Plan that compliments other strategy efforts | Aboriginal Cultural Capability Reform Program (ACCRP) | August 2023 Status - Completed The Aboriginal Cultural Capability Reform Program (ACCRP) is driving an agency-wide cultural reform agenda aimed at improving the cultural capability of the Department of Communities (Communities). Initial state-wide engagement with internal and external Aboriginal stakeholders has been completed in partnership with Aboriginal business, Kambarang Services, to inform the development of the draft Aboriginal Cultural Framework (the Framework) and draft Aboriginal Cultural Learning Strategy (Learning Strategy). The Framework and Learning Strategy will ensure Communities meets Priority Reform Area Three of the National Agreement on Closing the Gap, Transforming Government Organisations, and will operationalise how Communities will build, embed and maintain a culturally competent workforce and develop culturally capable systems, policies and practices that will enable better outcomes for Aboriginal people and communities. September 2022 The Aboriginal Cultural Capability Reform Program (ACCRP) was established by Communities to respond to the findings of the IPS Report. Between early 2020 and July 2021, functional reviews of all Communities divisions resulted in divisional and work realignment. The ACCRP renewed its focus on driving a department-wide cultural reform agenda, aimed at improving whole of life sustainable outcomes for Aboriginal children, people, and families, through improving Communities cultural competence and capability across the department. |
| Key Action 16 | Establish a series of data reporting mechanisms aligned with each system, strategy and project level implementation piece | Monitoring and Evaluation Framework | August 2023 Status - Completed The Project Portfolio Management (PPM) system is used to record all projects and programs of work and their alignment to State-level strategies or other Government priorities. The PPM facilitates progress and dashboard reporting from the project-level through to portfolio-level mapped to outcomes. September 2022 Communities commenced development of an integrated monitoring and evaluation framework (IMEF) and supporting tools to measure the progress and effectiveness of Communities-led whole-of-government strategies. The framework and supporting tools will provide Communities with oversight on: - progress made towards implementing the strategy - progress made towards achieving the strategy outcomes - the planned actions and how they link to the strategy outcomes - development of subsequent action plans and areas of focus. The principles, tools and processes established by IMEF will improve the consistency of the department’s approach to executing strategies, including coordination and collaboration with other strategies and sector partners. Through the development of logic models and monitoring and evaluation plans linked to whole of government outcomes, indicators and measures, Communities will be better able to communicate the intended impact of its activities, investments, methods employed for identifying success factors (community/sector engagement) and processes for the review and amendment of the strategies and their corresponding action plans. A key principle of the IMEF was to ensure all strategies were guided by the voices of those with lived experience across all phases of development, implementation, and evaluation. The IMEF sets the foundation for improving the quality and transparency of reporting against the progress and impact of Communities led strategies, upon which a comprehensive Strategy Reporting Lifecycle can be built. |
| Key Action 17 | Align each of the individual strategies to the whole of System Outcomes Framework | Communities Outcomes Framework | August 2023 Status – Ongoing Safe and Supported outcomes and alignment Safe and Supported: the National Framework for Protecting Australia’s Children 2021-2031 (Safe and Supported) is informing the prioritisation of efforts to reduce child abuse and neglect and its intergenerational impacts. Safe and Supported is underpinned by a Theory of Change and two targeted Outcomes Frameworks, developed in partnership with SNAICC and the Aboriginal and Torres Strait Islander Leadership Group. The National Coalition on Child Safety and Wellbeing was also consulted. The Outcomes Frameworks and Theory of Change align with the Aboriginal and Torres Strait Islander Child Placement Principle and the National Agreement on Closing the Gap to ensure all child protection reform work is aligned to achieve the same outcomes and realise the intended impact. September 2022 Communities will continue to develop project management plans and processes including outlining how projects deliver on the Communities outcomes framework. A robust Implementation Framework for child protection reform projects will be developed with clear governance and engagement with internal and external stakeholders as appropriate. |
| Key Action 18 | Develop individual action plans with clearly defined outcomes and timeframes for projects noted as ‘Future Directions’ within each strategy area | Communities Project Management templates and processes | August 2023 Status - Ongoing A robust project management framework has been rolled out and a reporting dashboard for tracking existing projects/programs that are contributing to child protection reform has been implemented. Communities will continue to refine the approach to managing child protection reform initiatives, including consideration of a whole-of Department Project Portfolio Management framework. September 2022 Communities will continue to develop project management plans and processes, such plans to include actions and outcomes. A robust Implementation Framework for child protection reform projects will be developed with clear governance and engagement with internal and external stakeholders as appropriate. |
| Key Action 19 | Clearly articulate stakeholder engagement at each level of system, strategy and project implementation | Communities Project Management templates and processes | August 2023 Status - Completed Stakeholder analysis and engagement is clearly prioritised and integrated in Communities’ Project Management processes throughout the project lifecycle. Stakeholder identification and analysis occurs in the ‘Initiate’ and ‘Planning’ phases of project/program scoping and ongoing feedback and engagement is facilitated throughout project/program ‘Delivery’ and ‘Close-out’ phases. Engagement strategy/method/frequency is informed by IAP2’s Public Participation Spectrum. September 2022 Communities will continue to develop project management plans and processes Stakeholder engagement strategies to be developed as part of the project planning process for each project. Note to include internal and external stakeholders. A robust Implementation Framework for child protection reform projects will be developed with clear governance and engagement with internal and external stakeholders as appropriate. |
| Theme Area 3: General systems and specific strategy actions priority three |  |  |  |
| Key Action 20 | Establish a workforce development program that caters for all levels of child protection worker, specialist roles and leadership | Future plans for a Workforce Strategy | August 2023 Status – In progress Work has commenced to develop a whole of Communities Workforce Planning Framework and Communities Capability Framework. Safe and Supported: the National Framework for Protecting Australia’s Children 2021-2031 (Safe and Supported) is informing the prioritisation of efforts to reduce child abuse and neglect and its intergenerational impacts. Communities commitments under Safe and Supported are directing efforts to ensure the future sustainability of the child protection workforce. This will include attraction and retention, capacity and capability approaches, embedding trauma-informed and culturally aware services and peer support through the delivery of specific projects, including: - WA Integrated Child Protection Practice Project - One Communities Family and Domestic Violence Informed Practice Approach September 2022 SCPU to work with Aboriginal Outcomes, LDC, SDOI and Strategic HR and universities to develop a frontline workforce development strategy, incorporating governance structure, process and workplan to embed continuous improvements. The strategy will capture all levels of child protection workers, specialist roles and leadership. Communities has established an Aboriginal Employees Network. |
| Key Action 21 | Ensure the workforce is well supported and cared for via a range of wellbeing strategies | Injury Prevention and Wellbeing team | August 2023 Status - Completed Communities has a dedicated Injury Prevention and Wellbeing Team responsible for the implementation of Communities’ various initiatives, including: - Wellbeing webinars and information awareness sessions; - Holistic wellbeing packs and the influenza vaccination program; - Thrive At Work Program targeting psychological and psychosocial wellbeing at work; - Communities’ Employee Assistance Program (EAP), including onsite EAP support. Work is currently underway to ensure improved support for Aboriginal and CaLD employees as part of the revised tender for employee assistance; and - Occupational Violence and Aggression program that informs the Residential Care Reform, Housing Reform project and support for Communities frontline/service delivery employees. Communities has also released: - the revised Work, Health, Safety and Wellbeing Policy in line with the Work Health and Safety Act 2020; and - the Prevention and Management of Adverse Workplace Behaviour Procedure supported by revisions to Communities’ safety reporting system to include ‘Confidential Reports’ – allowing staff to confidentially report health, safety and wellbeing concern. September 2022 Injury Prevention and Wellbeing team and their portal which provides health and wellbeing resources for staff. |
| Key Action 22 | Distinguish Continuous Quality Improvement efforts from Strategic efforts | Communities Project Management templates and processes | August 2023 Status - Completed A robust project management framework has been rolled out and a reporting dashboard for tracking existing projects/programs that are contributing to child protection reform has been implemented. Communities will continue to refine the approach to managing child protection reform initiatives, including consideration of a whole-of Department Project Portfolio Management framework which will contribute to distinguishing continuous quality improvement efforts from strategic reform work. September 2022 Communities will continue to develop project management plans and processes. |
| Key Action 23 | Develop and seek endorsement for the Implementation plans to support the new ACCO Strategy 2022-2031 | ACCO Strategy 2022-2032 | August 2023 Status - Completed The ACCO Strategy works on a flexible and phased approach to deliver on actions with initial priority actions outlined in the first of three implementation plans, ‘A Call to Action 2022 – 2024. The ACCO Strategy remains focused on delivering the key actions detailed in Implementation Plan One. Communities is currently progressing the delivery of the six actions for Implementation Plan One, which are about creating strong foundations upon which to build generational reform. Noting: - The Aboriginal Engagement Framework (AEF) is in the early stages of development with project planning occurring to identify and develop key pieces of work such as project deliverables and governance structures. - This Framework will guide Communities’ ways of working and engaging with Aboriginal people and communities to enable stronger relationships, enhance service delivery and include Aboriginal voices on local, place-based priorities and actions. - The AEF will be developed in a phased approach with phase one focusing on engagement with ACCOs and identified representatives from across the state to commence the co-design of the AEF. - The ACCO Commissioning Framework will strengthen the ACCO sector and support sustainable and socio-economic development. - The Framework will apply to future services being commissioned by the Department under the Delivering Community Services in Partnership Policy. - The ACCO Commissioning Framework will be completed by December 2023 and embedded across Communities' commissioning process from 2024 onwards. - This framework will be aligned to the forthcoming State Commissioning Strategy and the existing Communities Commissioning Plan. - Procurement planning is underway for the engagement of an external partner to co-develop an Accountability, Monitoring and Evaluation Framework for the Strategy. - Communities are in the planning phase of developing an agency-wide shared decision-making body through implementation of a working group made up of regional staff and representatives from local ACCOs and Aboriginal businesses. September 2022 Communities ACCO Strategy 2022-2032 was launched on the 3 August 2022. The ACCO Strategy aims to transform the way that Communities’ services for Aboriginal people are designed, funded and procured, and its implementation will focus on effective co-design with a broad representation of ACCOs from across WA. The ACCO Strategy acknowledges the pivotal role played by Aboriginal Organisations in delivering culturally secure services to Aboriginal people across the State. It recognises outcomes are better when Aboriginal people are provided place-based, locally led and culturally safe services to Aboriginal people. The ACCO Strategy seeks to improve Communities’ commissioning and delivery of services to Aboriginal children, families and communities, and to support ACCOs to increase their capacity to deliver place-based, culturally appropriate services across WA. The ACCO Strategy aligns directly to a number of Priority Reform Areas and Socio-Economic targets identified within the National Agreement on Closing the Gap and will assist Communities in meeting its commitment as a signatory to the Agreement. Communities is the lead agency for the Early Childhood Care and Development Sector Strengthening Plan and the ACCO Strategy identifies, builds capability and develops opportunities for ACCOs to provide services to Aboriginal people across these areas. The ACCO Strategy focuses on three key pillars; cultural safety and governance, respectful partnerships and economic opportunities. |
| Key Action 24 | Co-design and implement a dedicated Aboriginal Family Safety Strategy as per Path to Safety: Western Australia’s Strategy to Reduce Family and Domestic Violence 2020-2030 and the At-Risk Youth Strategy 2022-2027 | Development of the Aboriginal Family Safety Strategy Development of the At Risk Youth Strategy | August 2023 Status - Completed Aboriginal Family Safety Strategy The Aboriginal Family Safety Strategy 2022- 2032 (the Strategy) was released by the Minister for Aboriginal Affairs and the Minister for Prevention of Family and Domestic Violence in December 2022. The Strategy provides a ten-year framework that commits Government, Aboriginal people and the wider community to preference Aboriginal led responses to family violence, with a focus on healing, recognising and supporting the unique roles and responsibilities of men and boys, transforming service provision to drive localised, sustainable and culturally safe solutions, and to use culture as the guiding frame for prevention and early intervention. Importantly, the Strategy is a cross-Government initiative and forms part of State Government’s response to Outcome 13 of the National Agreement on Closing the Gap – that Aboriginal and Torres Strait Islander families and households are safe. The State Government continues to work with Aboriginal communities and stakeholders to develop solutions, prioritising Aboriginal values, beliefs, culture, identity, and knowledge systems in holistic responses to Aboriginal family safety. Implementation planning is currently underway, guided by the Strategy's principles, including being Aboriginal-led, designed in partnership, place-based, responsive to different groups and people and reflective of new and better ways of working. Implementation of the Strategy is also happening in the context of the Commonwealth Government’s commitment to develop an Aboriginal and Torres Strait Islander Action Plan as part of the National Plan to End Violence Against Women and Children 2022-2032. Status - Completed The At-Risk Youth Strategy 2022 - 2027 The At-Risk Youth Strategy 2022 – 2027 was released in September 2022. Communities is working in partnership with the Youth Affairs Council of Western Australia (YACWA) on the implementation of the At-Risk Youth Strategy. A multi-Agency Reference Group, including young people with lived experience. has been established to oversee the development and implementation of the First Action Plan. The four Focus Areas of the Strategy are: - Focus Area One: Partnerships, collaboration and integrated responses. - Focus Area Two: Targeted initiatives to improve long term outcomes. - Focus Area Three: Strengthening the services system for at risk young people. - Focus area Four: Services and supports for Aboriginal young people. September 2022 Aboriginal Family Safety Strategy The Department of Communities commenced work on the development of the Aboriginal Family Safety Strategy in mid-2021. To ensure the project is driven by Aboriginal voices, an Aboriginal consultant has been engaged to lead the drafting of the Strategy. A comprehensive community and stakeholder engagement process was undertaken to inform the Strategy, with over 550 Aboriginal people consulted across the State. A consultation draft of the Strategy was released for public comment from mid-March to mid-April, which included further targeted engagement with Aboriginal community and stakeholders. The Strategy is anticipated to be finalised and publicly released later in 2022. At Risk Youth Strategy 2022-2027 The State Government will continue to improve long-term, sustainable outcomes for at risk young people through the development and implementation of an At Risk Youth Strategy. The At Risk Youth Strategy will provide the mechanism for collective effort across government agencies, peak bodies and the community services sector to improve outcomes for highly vulnerable young people. A focus area in the draft Strategy captures the implementation of the 2021 election commitment to permanently extend Home Stretch. The At Risk Youth Strategy 2022-2027 was released by Communities and the Youth Affairs Council of WA (YACWA) on 19 September 2022. |
| Key Action 25 | Rationalise the EIFS strategy 2016 as implemented | Early Intervention and Family Support Strategy | August 2023 Status - Completed The EIFS new Regional Service Model was finalised in December 2022. The model was developed in consultation with the community, particularly Aboriginal stakeholders across each of the three selected regional sites. The model has now been implemented in the South West region as of 1 March 2023 and will be commencing in the Pilbara and East Kimberley regions on 1 July 2023. Other EIFS programs including the Family Support Network, Intensive Family Support Service, and Aboriginal In-home Support Service have received ongoing funding. The contracts have been extended for one year until 30 June 2024 and are due to be newly commissioned with new contracts commencing in July 2024. A commissioning process will be initiated later this year. September 2022 Communities will be undertaking co-design around regional expansion of the Earlier Intervention Family Support Service (EIFSS), and funding pilots of regional models to inform future service delivery. This model will test a more holistic and integrated service model and continuum of services; a lead or equal role for ACCOs in contract partnership; integration of Aboriginal ways of working and more culturally responsive practices; a co-designed Theory of Change and clear program logic and outcomes framework; and flexible and innovate place/region-based design and procurement approach. |
| Theme Area 4: Medium-term 12 – 24 months |  |  |  |
| Key Action 26 | Undertake an appreciative enquiry style Audit of the Commissioning Plan 2021-2022 once completed | supported | August 2023 Status update – Completed The Department of Communities will update the Commissioning Plan and publish updates every two years on our website. Each update to the Commissioning Plan will reflect learnings from sector stakeholder engagement and government priorities. With the release of the 2021 Commissioning Plan, Communities set an ambitious direction for the future of its commissioning cycles. The actions undertaken during 2021 and 2022 have informed the development of a second iteration of the commissioning plan for 2023 including incorporation of commissioning approaches for services procured under the Delivering Community Services in Partnership Policy expiring up to 31 December 2024. September 2022 Nil update |
| Key Action 27 | Review the Communities’ Implementation Framework once established | supported | August 2023 Status – In progress The Specialist Child Protection Unit (SCPU) established the SCPU Project Management Office in October 2022. A robust project management framework has been rolled out and a reporting dashboard for tracking existing projects/programs that are contributing to child protection reform has been developed. Projects and Programs underway that are contributing to child protection reform are reviewed at regular intervals via status reports. Communities will continue to refine the approach to managing child protection reform initiatives, including consideration of a whole-of Department Project Portfolio Management framework. September 2022 Nil update |
| Key Action 28 | Undertake service system review within youth services as intended within the At-Risk Youth Strategy 2021-2026 | At Risk Youth Strategy | August 2023 Status – In progress - Communities commenced a staged Statewide rollout of Home Stretch WA in mid-2022- In progress. - Home Stretch WA provides the opportunity for young people leaving out of home care at 18 with the option to continue to receive support up until the age of 21. - The Home Stretch WA model was co-designed with young people with lived experience of transitioning from care, with a particular focus on the needs of young Aboriginal people and their families. - A key element of support through the program is to help young people to build and maintain connections to their family, community and country. - Communities is delivering an interim service provision model to deliver the Home Stretch WA program across the state through to August 2024. - A Registration of Interest process, targeting ACCOs, is being used to gauge the level of interest of organisations to deliver Home Stretch WA across the state. - Communities has commissioned one ACCO to deliver the program to young Aboriginal people leaving care in metropolitan Perth, and six ACCOs have been commissioned across the Kimberley and Pilbara to deliver place-based support. - Commissioning of ACCOs to deliver Home Stretch is underway in the Mid-West Gascoyne, Wheatbelt and Goldfields regions. September 2022 The McGowan Government will continue to improve long-term, sustainable outcomes for at risk young people through the development and implementation of the At-Risk Youth Strategy 2022-2027. The At-Risk Youth Strategy will provide the mechanism for collective effort across government agencies, peak bodies and the community services sector to improve outcomes for highly vulnerable young people. A focus area in the draft Strategy captures the implementation of the 2021 election commitment to permanently extend Home Stretch. |
| Key Action 29 | Implement 10 Year Roadmap as per plans developed throughout the project | 10 Year Roadmap to Reduce the Number of Aboriginal Children in Care - currently under development | August 2023 Status – In progress The Roadmap is still under development and due to be delivered by SNAICC in mid 2023 (see update for Key Action 9). Communities has been working closely with SNAICC and key government partner agencies throughout the project to ensure: - the project is driven by Aboriginal people, for Aboriginal people and will truly reflect their needs, aspirations and solutions (see Key Action 9) - rigorous project planning and governance. SNAICC and Communities developed project plans and established governance groups including a Roadmap Aboriginal Advisory Group, a Roadmap Internal Working Group and Roadmap Government Reference Group. Communities has prepared Roadmap briefings for key Government Aboriginal advisory bodies. The Roadmap is WA’s response to Closing the Gap Target 12 and Safe and Supported: National Framework for Protecting Australia’s Children 2021-2031. SNAICC is scheduled to deliver a draft Roadmap, first Action Plan and a proposed governance mechanism to guide implementation by 31 July 2023, for WA Government consideration. September 2022 Communities has engaged SNAICC and will work together to undertake a consultative process to develop the Roadmap throughout 2022. |
| Key Action 30 | Implement and monitor the required changes across the sector as determined within the Commissioning Plan 2021-2022 | supported | August 2023 Status update – Completed The 2023 Communities Commissioning Plan continues the commitment to continue to work in partnership with other government agencies and the community services sector, community housing sector and ACCOs to inform a commissioning approach. The implementation of the Commissioning Plan is monitored by the Commissioning Project Control Group (PCG) which provides high level leadership and strategy to manage the delivery of commissioning across Communities. The PCG will oversee all streams of commissioning across Communities at a system-level and identify synergies between the streams. The PCG will also review and evaluate the pressures on community service organisations and, where possible, minimise unnecessary administrative burdens. September 2022 Nil update |