## Contract Info and Criteria
Consultant Performance Report (cost manager contracts) | [7 empty] | Version 3
TRIM Ref: 07888770
Works Document Library Number: 1627
General Information | [7 empty] | Effective date: 1 July 2025
Project or Work Order Name
Project or Work Order No. (as per Ready Contracts or Mainsaver)
Current Project Status | Project Handover
Reporting Officer
Reporting Officer Position Title
Approving Officer (Level 8 or higher)
Approving Officer Position Title
Date of Report (dd/mm/yyyy) | 2025-07-01
Commission/Contract Details
Consultant Legal Entity Name
Consultant Engagement Method | Cost Management Services Panel A 2017
Consultant's Role
Contract or Purchase Order Number (as per Ready Contracts or Mainsaver)
Contract Award Date (dd/mm/yyyy) | 2025-01-01
Consultant's Representative Name
Reason for performance report | Construction Practical Completion
Quality of Cost Management - contract history
A. Accuracy of Cost Management during the design phase | Construction Cost Estimate (ex GST) |  | Approved Construction Budget $ (ex GST) |  | Construction Cost Estimate minus Approved Budget ($) | as a % of Budget (Excellent = 0%, otherwise Unsatisfactory) | Weighted Average SD 10% DD 30% CD 60%
Agreed Construction Cost at appointment of Cost Consultant - including design contingency (at PDP, if completed) | 1000
Construction cost estimate at Schematic Design |  |  |  |  | 0 | #DIV/0!
Construction cost estimate at Design Development |  |  |  |  | 0 | #DIV/0!
Construction cost estimate at Contract Documentation (PTE) |  |  |  |  | 0 | #DIV/0!
Comment:
B. Accuracy of pre-tender estimate compared to market prices at tender |  |  | Construction cost estimate at Contract Documentation (PTE) |  | 2nd lowest tender minus PTE $ | As a % of PTE (Good - with BOQ <5%, no BOQ <10%; Excellent <2.5%, otherwise unsatisfactory)
Was a Bill of Quantity prepared? | No
2nd lowest tender |  |  | 0 |  |  |  | 0
Accepted tender price
Comment:
C. Accuracy of Cost Management during the construction stage |  |  | Accepted Tender Price |  | Variations due to Measurement Errors as a % of the Accepted Tender Price (Good <1%, Excellent <0.5%)
Variations not due to Measurement Errors (latent conditions, documentation error, client request)
Variations due to measurement errors (ie BOQ error) |  |  | 0
Final Cost at Practical Completion (accepted tender price plus variations) | 0
Comment:
Performance Measurement Criteria
Project Managers are requested to give a score for each of the five criteria. For guidance on completing each criteria, go to the Guide Notes. Where your score for any criterion is "Excellent", "Unsatisfactory" or "Not Applicable" you must detail the reasons for the score.
Quality of Cost Management (35%) | Unsatisfactory | Marginal | Good | Very Good | Excellent | N/A | SCORE
| 1 | 2 | 3 | 4 | 5 | 0 | 3
Comments
Quality of Documentation and Service (35%) | Unsatisfactory | Marginal | Good | Very Good | Excellent | N/A | SCORE
| 1 | 2 | 3 | 4 | 5 | 0 | 3
Comments
Time Management (10%) | Unsatisfactory | Marginal | Good | Very Good | Excellent | N/A | SCORE
| 1 | 2 | 3 | 4 | 5 | 0 | 3
Comments
Resource Management (10%) | Unsatisfactory | Marginal | Good | Very Good | Excellent | N/A | SCORE
| 1 | 2 | 3 | 4 | 5 | 0 | 3
Comments
Communications and Relationships (10%) | Unsatisfactory | Marginal | Good | Very Good | Excellent | N/A | SCORE
| 1 | 2 | 3 | 4 | 5 | 0 | 3
Comments

## Summary and Additional Comments
Consultant Performance Report Summary (cost manager contracts)
General Information
Project or Work Order Name | 0
Project or Work Order Number | 0
Current Project Status | Project Handover
Reporting Officer | 0
Reporting Officer Position Title | 0
Approving Officer | 0
Approving Officer Position Title | 0
Date of Report | 2025-07-01
Commission/Contract Details
Consultant Legal Entity Name | 0
Consultant Engagement Method | Cost Management Services Panel A 2017
Consultant's Role | 0
Contract or Purchase Order Number | 0
Consultant's Contract Award Date | 2025-01-01
Consultant's Representative Name | 0
Reason for performance report | Construction Practical Completion
Cost Estimate Accuracy | Variance $ |  | Variance %
Construction Cost estimate at SD to Approved Construction Budget | 0 |  | #DIV/0!
Construction Cost estimate at DD to Approved Construction Budget | 0 |  | #DIV/0!
Construction Cost estimate at CD to Approved Construction Budget | 0 |  | #DIV/0!
2nd tenderer's price to PTE
Measurement errors at Practical Completion to PTE | 0
Overall Performance Rating
Performance Score | 60%
Excellent >=86% | Very Good 75% - 85.9% |  | Good 60% - 74.9% | Marginal 46% - 59.9% | Unsatisfactory <46%
Well above the acceptable standard of performance | Often exceeds the acceptable standard of performance |  | Meets the acceptable standard of performance required by the contract | Mostly meets the acceptable standard of performance but has some weaknesses | Well below the acceptable standard of performance
Criteria | Weighting | Rating | Comments
Quality of Cost Management | 35% | 3 | 0
Quality of Documentation and Service | 35% | 3 | 0
Time Management | 10% | 3 | 0
Resource Management | 10% | 3 | 0
Communications and Relationships | 10% | 3 | 0
Comments by Reporting Officer
Comments by Approving Officer
Date report sent to Consultant: |  |  | Email and signed CPR to Consultant is contained in project TRIM folder
Comments by Consultants (including, what could Finance have done differently to improve the outcome of the project)
Approving Officer's reply to consultant's comments
Date response sent to Consultant: |  |  | Correspondence contained in project TRIM folder
Final Agreed Performance Rating (changes made in consultation with the Consultant (if applicable: detail original score and criteria ratings that have changed as a result of the Consultant's right of response))
Reporting Officer Name |  | Position Title |  | Signature |  | Date
0 |  | 0
Approving Officer Name |  | Position Title |  | Signature |  | Date
0 |  | 0
Print summary
PDF summary (to send to consultant)
PDF complete document

## Guide Notes
GUIDE NOTES
Quality of Cost Management (35%)
The Reporting Officer is to use their discretion in evaluating this criterion and must provide comments to support the assessment rating. To assist the Reporting Officer, a guide is included in the Performance Report template with questions that should be considered when assessing the quality of cost management at each stage of the project. At business case and PDP stage • Did the cost estimate use appropriate regional loadings and appropriate escalation of costs? At design stage • Did the cost estimate at each stage of schematic design, design development or contract documentation vary from the agreed construction cost? • If so, any variance (due to scope change or design changes for example) requires client approval and amendment to the budget. • If this is the case, the score is 5 (“Excellent”); if not, the score is zero (“Unsatisfactory”). • The final score for the design stage is a weighted average of Schematic Design (10%), Design Documentation (30%) and Contract Documentation (60%) At tender stage • The accuracy of the cost estimate at the construction contract tender stage (the Pre-Tender estimate) is assessed by comparing it with the tender price of the second lowest tenderer. • Anecdotally, the second lowest tenderer (of the current procurement practice of seeking prices from four shortlisted tenderers) is considered to most accurately represent the market price. • A cost estimate is considered “Good” (score of 3) if the PTE is within 5% of the 2nd lowest tenderer (if a BOQ is used), or within 10% (if a BoQ is not used). • If the cost estimate is not within these ranges, it is considered “UnGood” (score of zero) • In order for a cost estimate to be considered “Excellent” (score of 5), the PTE is to be within a range of 2.5% of the 2nd lowest tenderer. • The Reporting Officer should also consider the range of tender prices when assessing the accuracy of the PTE. At practical completion stage • The accuracy of the cost estimate at the practical completion stage is assessed by identifying any variations to the Accepted Tender Prices that were a result of measurement errors (in the BOQ) made by the Cost Manager. • These measurement errors do not include varations that were due to scope change, latent conditions or documentation errors attributed to the architect. • Variations to the Accepted Tender Price due to measurement error of 1% or less are considered “Good” (score of 3) • If not, the cost management is considered “UnGood” (score of zero). • In order to achieve an “Excellent” rating (score of 5), the variation is to be 0.5% or less.
Quality of Documentation and Service (35%)
Quality of Documentation * documents prepared for any contract/s are accurate and BOQ's (if relevant): * adhere to the ASMM 6th edition of state the Principal's required method of measurement * has been checked for errors - the Project Manager is to form a view if the pre-tender cost estimate has been checked for errors (ie verified by a third party within the firm, have they priced their own bill, or do they utilise ISO9001 Quality accreditation?) * resulting in no claims by the contractor in this regard Use of Policies, Procedures and Initiatives Policies, procedures and initiatives will generally be a measurement of the Consultant’s, however the following should be considered: • Construction contract documents comply with and where appropriate include relevant Government and Department policies and requirements. • Compliance with consultancy contract including relevant Government and Department policies and requirements. Standard of Service Standard of service will generally be measured against the technical, financial, and reporting requirements set out in the conditions of the contract. In particular, the following should be considered: • Compliance with the specified brief. • Financial considerations. • Quality of the provision of advice including extent to which review and rework is required. • Progress payment and variation recommendations. • Attendance at meetings
Time Management (10%)
Consultant contracts that are significant should have an agreed work plan with milestones for intermediate phases of the work as well as a finishing time for the overall contract. In assessing the Consultant’s time management performance the following should be considered: • Ability to meet (or manage) the time programme. • Resourcing. • Timely advice and progress reports. • Fair consideration of delays caused by other parties.Delays by the Principal or other parties, outside the Consultant’s control.
Resource Management (10%)
The Consultant’s ability to assign appropriate staff to the project and then to ensure cooperative and effective performance including: • Resourcing and management of personnel. • Suitability of staff. • Quality of services.
Communications and Relationships (10%)
The following should be considered when assessing communications and relationships: • Management approach that fosters continuous improvement, self-assessment and general industry monitoring. • Partnering principles with clients, subconsultants, contractors and suppliers. • Non-adversarial approach in managing and resolving issues. | BACK

## BMW Workings (hidden)
| Unsatisfactory | Marginal | Good | Very Good | Excellent | N/A | Assessment | Score | Rating
| 45% | 59% | 74% | 85% | [7 empty] | Table 1
| 1 | 2 | 3 | 4 | 5 | N/A
[7 empty] | a. | b. | c. | d. | e. | f. | g. | h. | i. | j.
[7 empty] | result | score | rating | weighting | include = 1 | weight (unadjust) | weight (adjust) | score (unweight) | score (weight) | adj score
Quality of Cost Management | [6 empty] | 3 | 3 | Good | 35% | 1 | 35% | 35% | 21% | 35% | 1.05 |  | 21%
Quality of Documentation and Service | [6 empty] | 3 | 3 | Good | 35% | 1 | 35% | 35% | 21% | 35% | 1.05 |  | 21%
Time Management | [6 empty] | 3 | 3 | Good | 10% | 1 | 10% | 10% | 6% | 10% | 0.3 |  | 6%
Resource Management | [6 empty] | 3 | 3 | Good | 10% | 1 | 10% | 10% | 6% | 10% | 0.3 |  | 6%
Communications and Relationships | [6 empty] | 3 | 3 | Good | 10% | 1 | 10% | 10% | 6% | 10% | 0.3 |  | 6%
Total | [7 empty] | 15 |  | 100% |  | 100% | 100% | 60% | 100% | 3 | Good | 60%
Count total | [6 empty] | b.: 5; j.: 5 |  | 5
Exclude criteria if N/a
Number of criteria included | [6 empty] | j.: 60%
Explanation of Table 1
Average score | [6 empty] | a.: a.; b.: this is inputted into the Contract Info and Criteria sheet
[7 empty] | b. | this is the score (ie if a. is N/A, then the score = zero)
Rating | [6 empty] | a.: c.; b.: the rating
[7 empty] | d. | the weighting for each section
[7 empty] | e. | a field to help with calculating - adjusted weighting
DROP DOWN BOXES | [6 empty] | a.: f.; b.: unadjusted weighting
Relevant Panel | [6 empty] | a.: g.; b.: adjusted weighting (the N/A is distributed proportionally)
Cost Management Services Panel A 2017 | [6 empty] | a.: h.; b.: actual score - unweighted
Cost Management Services Panel B 2017 | [6 empty] | a.: i.; b.: actual score - weighted (the N/A is distributed proportionally)
Open Tender | [6 empty] | a.: j.; b.: adjusted score (total / rating / rating %)
Other
Status
Project Planning
Schematic Design | [6 empty] | a.: was a BQ prepared?
Design Documentation
Contract Documentation | [6 empty] | a.: Yes
Construction Tender Award | bar: a.
In Construction
Project Handover | [6 empty] | a.: Ratings
In Defects Liability Period
Finalisation of Contract | [6 empty] | a.: 1; b.: Unsatisfactory
[7 empty] | 2 | Marginal
Reason for report | [6 empty] | a.: 3; b.: Good
Construction Contract Award | [6 empty] | a.: 4; b.: Very Good
Construction Practical Completion | [6 empty] | a.: 5; b.: Excellent
Contract Completion | [6 empty] | a.: N/A; b.: Not Applicable
Exception Reporting
Other
Data Entry
Calculation for Cost Estimation |  | absolute | bar: a.
variance to Agreed Construction Cost - SD | #DIV/0! | #DIV/0! | #DIV/0!
variance to Agreed Construction Cost - DD | #DIV/0! | #DIV/0! | #DIV/0!
variance to Agreed Construction Cost - CD | #DIV/0! | #DIV/0! | #DIV/0!
2nd lowest tender |  |  | 0
2nd lowest tender |  |  | 0
Variations due to Measurement error (ie BOQ error) |  |  | 0
Variance to the Agreed Construction Cost in Planning Stage |  |  |  |  | Score | Definition
0.01% | 5 |  |  |  | 1 | Well below the acceptable standard of performance. Comments must be provided to explain how the supplier performed so poorly.
otherwise | 0 |  |  |  | 2 | Mostly meets the acceptable standard of performance but has some weaknesses.
[5 empty] | 3 | Meets the acceptable standard of performance.
PTE vs Accepted tender price (with BOQ) |  |  |  |  | 4 | Often exceeds the acceptable stand of performance.
2.5% | 5 |  |  |  | 5 | Well above the acceptable standard of performance. Comments must be provided to explain how the supplier consistently exceeded the requirements.
5% | 3 |  |  |  | N/A | Comments must be provided to explain why this criterion is not applicable
10% | 0
>10% | 0
0
PTE vs Accepted tender price (no BOQ)
2.5% | 5
10% | 3
15% | 0
>15% | 0
0
Variations due to Measurement error (ie BOQ error) | Scores
0.5% | 5
1% | 3
5% | 0
10% | 0
0

## Data Entry (hidden)
Consultant Performance Report Summary Database
General information and Contract details | [9 empty] | Quality of Cost Management |  |  | Quality of Documentation and Service |  |  | Time Management |  |  | Resource Management |  |  | Communications and Relationships |  |  | Performance Rating | Performance Score | Reporting and Approving Officer Comments | Consultant Comments
Relevant Panel | Project Name | Project Number | Reporting Officer | Approving Officer | Date report completed | Consultant Name | Consultant Type | Contract Number | Reason for Report | Rating | Score | Percentage | Rating | Score | Percentage | Rating | Score | Percentage | Rating | Score | Percentage | Rating | Score | Percentage
Cost Management Services Panel A 2017 | 0 | 0 | 0 | 0 | 2025-07-01 | 0 | 0 | 0 | Construction Practical Completion | Good | 3 | 21% | Good | 3 | 21% | Good | 3 | 6% | Good | 3 | 6% | Good | 3 | 6% | Good | 60% |  | 0