## Index
Carbon Innovation Grants Program Feasibility Studies Round 3 - 2026
1 | Project costs
2 | Project funding
3 | Milestones and expected expenditure
4 | Projected operating emissions and costs
5 | Viability and Impacts
6 | Financial Returns
7 | Potential for wider adoption
8 | Cashflow projections
9 | Validation
10 | Project Summary
11 | CIGP parameters
12 | Assumptions
13 | In-kind Contribution
14 | Merit criteria
15 | Eligible costs

## Project Model
Carbon Innovation Grants Program Feasibility Studies Round 3 - 2026
1. Project costs (exclude GST)
Description of each cost item | All costs | % Eligible | Eligible costs | Source or reasoning behind value (Attach clearly labelled evidence in SmartyGrants where needed)
In-kind contribution (from In-kind tab) | 300 | 100% | 300
Technology Options Assessment | 50000 | 100% | 50000 | Consultant quoted study of world wide best practice CCUS technology (Attachment 4)
Baseline field testing of stack emissions | 50300 | 100% | 50300 | Consultant quote (Attachment 8)
Lab testing carbon capture and concentration technology | 150000 | 100% | 150000 | Lab quote (Attachment 7)
Lab testing carbon addition to cement technology | 150000 | 100% | 150000 | Lab quote (Attachment 9)
Lab testing treated cement strength and quality | 50000 | 100% | 50000 | Inhouse testing laboratory
Financial modelling | 60000 | 100% | 60000 | Consultant quote (Attachment 10)
Preparation of final report | 10000 | 100% | 10000 | Consultant quote (Attachment 10)
0
Work already done | 25000 | 0% | 0
Total | 545300 |  | 520300
2. Project funding (exclude GST)
Source | Amount | % of all costs | Source or reasoning behind value (Attach clearly labelled evidence in SmartyGrants where needed)
CIGP request | 200000 | 36.68% | Refer to application
Other WA government grants | 10000 | 1.834% | R&D grant (attachment 1)
Other grants |  | 0%
Cash contribution from applicant | 310000 | 56.85% | Facility Budget 2023-24
Funds from other investors |  | 0%
Debt |  | 0%
In-kind contribution from applicant | 0 | 0%
In-kind contribution from others | 300 | 0.05502%
Other (Describe) |  | 0%
Total funding | 520300 | 95.42%
Unaccounted for | 25000 | 4.585%
Maximum buffer available | 50000 | 9.169% | Additional funding available if necessary - Line of credit from XYZ bank
Unaccounted funds <= buffer? |  | TRUE | Is there enough money, with the buffer, for the project to complete?
3. Milestones and expected expenditure
Milestone Number and Name | Project Deliverable |  | Eligible milestone costs (excl in-kind) | Assumed In-kind contribution per milestone | Total eligible milestone cost | Assumed CIGP payment | CIGP Percentage % | Date
0 - Project Commencement | Site access and project plan | [6 empty] | 2027-07-01
1 - Initiation | Project Works Start |  | 20000 |  | 20000 | 7687.8724 | 38.44%
2 - Options Assessment | Options Assessment Complete |  | 55000 |  | 55000 | 21141.649 | 38.44%
3 - Field testing | Field Studies Complete |  | 200000 |  | 200000 | 76878.7238 | 38.44%
4 - Lab testing | Lab studies Complete |  | 183000 | 300 | 183300 | 70459.3504 | 38.44%
5 - Financial assessment | Financial Modelling complete |  | 40000 |  | 40000 | 15375.7448 | 38.44%
6 - Final feasibilibity report | Final Report draft and Peer Review (see last row of this table) |  | 10000 |  | 10000
7 | Project Completion |  | 12000 |  | 12000 | 4612.7234 | 38.44%
8 |  |  |  |  | 0 | 0
9 |  |  |  |  | 0 | 0
10 |  |  |  |  | 0 | 0
11 |  |  |  |  | 0 | 0
12 | Final Report Submitted |  | #N/A |  | #N/A | 10000
Total |  |  | 520000 | 300 | 520300 | 206156.0638 | 39.62%
The final milestone must include a deliverable for final report. This can be at the conclusion of the project or 6 months post the end of the project - a cost must be attributed to the final report.
Note that feasibility studies must be completed in two years from project start to final report
4. Projected Operating Emissions and Costs of Project Built if the Feasibility Study is Successful
Scope | Inputs and outputs |  |  |  |  | Emissions or (sinks) in T CO2-e/yr |  | Costs or (revenue) in $/yr |  | Source or reasoning behind value
| Source |  | Units | Baseline | After full-scale deployment | Baseline | After full-scale deployment | Baseline | After full-scale deployment | (Attach clearly labelled evidence in SmartyGrants where needed)
Carbon emission sources
Scope 1 | Mobile Plant Diesel Use |  | KL/yr | 60 | 60 | 163.0464 | 163.0464 | 116868 | 116868 | Quarrying of raw materials, factory transport
Scope 1 | Mobile Plant Petrol Use |  | KL/yr |  |  | 0 | 0 | 0 | 0
Scope 1 | Stationary Plant Fuel Use |  | KL/yr |  |  | 0 | 0 | 0 | 0
Scope 1 | Process emissions |  | T CO2-e/PU | 0.535 | 0.535 | 26750 | 26750 |  |  | Emissions from heating limestone (attachment 3)
Scope 2 | Electricity use |  | MWh/yr |  |  | 0 | 0 | 0 | 0
Scope 2 | Natural Gas use |  | GJ/yr | 1000000 | 1000000 | 51530 | 51530 | 10480000 | 10480000 | Emissions from gas used to heat limestone
Scope 1 | Fugitive emissions | [6 empty] | 0 | 0
Scope 1 or 2 | Other Emissions
Less carbon sinks
Sink | CCUS (Carbon Capture, Use & Storage) | [5 empty] | -77000 |  |  | Proposed CCUS from burning gas and process emissions
Sink | CCUS (Carbon Capture, Use & Storage) | [7 empty] | 50000 | Annual operating costs for CCUS
Sink | Carbon Credits Generated |  | T CO2-e/PU |  |  | 0 | 0 | 0 | 0 | Carbon credits purchased to achieve carbon neutrality
Sink | Carbon Credits Purchased |  | T CO2-e/PU |  |  | 0 | -2000 | 0 | 60000 | Carbon credits purchased to achieve carbon neutrality
Other costs or revenue
Other Operating Costs
| Other Revenue or Savings | [7 empty] | -250000 | Revenue from carbon neutral cement premium
Totals | [5 empty] | 78443.0464 | -556.9536 | 10596868 | 10456868
5. Viability and Impact |  |  |  | Unit | Amount | Source or reasoning behind value
(Attach clearly labelled evidence in SmartyGrants where needed)
Production life |  |  |  | Years | 20 | Cement plant life
Estimated emissions from project construction (Scope 1 and Scope 2) |  |  |  | T CO2-e | 50000 | Concept estimate (attachment 10)
Annual emissions saving from project. |  |  |  | T CO2-e/year | 79000
Lifetime Emissions saved |  |  |  | T CO2-e | 1530000
6. Financial Return |  |  |  | Unit | Amount | Source or reasoning behind value
Capital cost full scale |  |  |  | $ | 1300000 | Industry estimate (attachment 2)
Discount rate (use real rate = nominal rate - inflation) |  |  |  | % | 3%
Simple Payback |  |  |  | Years | 9
Internal Rate of Return (IRR) (real rate, for nominal, add inflation rate) |  |  |  | % | 8.762%
Net Present Value (NPV) in current year dollars |  |  |  | $ | 3382846.4805
7. Potential for wider adoption |  |  |  | Unit | Amount | Source or reasoning behind value
How many similar sized projects do you expect to be built by 2035 because of this feasilibity study? |  |  |  | Units | 2
8. Cashflow projections
Derived NPV and IRR calculations -no edits required
| Operating Costs |  | Net Saving
Year | Baseline Forecast | New Forecast | Project impact | Cumulative | Payback
0 |  |  | -1300000 |  | -1300000
1 | 10596868 | 10456868 | 140000 | 140000 | -1160000
2 | 10596868 | 10456868 | 140000 | 280000 | -1020000
3 | 10596868 | 10456868 | 140000 | 420000 | -880000
4 | 10596868 | 10456868 | 140000 | 560000 | -740000
5 | 10596868 | 10456868 | 140000 | 700000 | -600000
6 | 10596868 | 10456868 | 140000 | 840000 | -460000
7 | 10596868 | 10456868 | 140000 | 980000 | -320000
8 | 10596868 | 10456868 | 140000 | 1120000 | -180000
9 | 10596868 | 10456868 | 140000 | 1260000 | -40000
10 | 10596868 | 10456868 | 140000 | 1400000 | 100000
11 | 10596868 | 10456868 | 140000 | 1540000 | 240000
12 | 10596868 | 10456868 | 140000 | 1680000 | 380000
13 | 10596868 | 10456868 | 140000 | 1820000 | 520000
14 | 10596868 | 10456868 | 140000 | 1960000 | 660000
15 | 10596868 | 10456868 | 140000 | 2100000 | 800000
16 | 10596868 | 10456868 | 140000 | 2240000 | 940000
17 | 10596868 | 10456868 | 140000 | 2380000 | 1080000
18 | 10596868 | 10456868 | 140000 | 2520000 | 1220000
19 | 10596868 | 10456868 | 140000 | 2660000 | 1360000
20 | 10596868 | 10456868 | 140000 | 2800000 | 1500000
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
END OF MODEL

## Outputs and Inputs
Carbon Innovation Grants Program Feasibility Studies Round 3 - 2026
Project: Assess the feasibility of carbon capture and use from a cement kiln
Description: This case example seeks funding to undertake a feasibility study for carbon emissions capture from a cement and lime factory and conversion of the captured emissions into a solid material that can be incorporated into cement products (Carbon Capture and Use or CCUS).
9. Validation |  | Value
Is CIGP request not less than $50,000? |  | TRUE
Is CIGP request not greater than $500,000? |  | TRUE
Is CIGP request plus other WA Government grants not greater than 50% of eligible costs? |  | TRUE
Are sources identified for all project costs? |  | TRUE
Are all costs allocated to milestones? |  | TRUE
Are all CIGP funds spent within 2 years? |  | TRUE
Is IRR > Investment threshold? |  | TRUE
10. Project summary | Units | Feasibility Study | Optional Comments
Eligible feasibility study cost | $ | 520300
CIGP request | $ | 200000
CIGP request as percentage of eligible costs | % | 38.44%
Project life in months | months | 22
Annual emissions reduction tonnes of CO2-e | T CO2-e/year | 79000
Annual emissions reduction relative to baseline | % | 100.7%
Lifetime CO2-e tonnes saved | T CO2-e | 1530000
Lifetime capital cost per tonne of CO2-e avoided | $/T CO2-e | 0.84967
Minimum permanence of abatement (years) | years | 10
Potential scale of abatement from wider adoption | T CO2-e | 3060000
Total non-grant funds including in-kind contributions | % | 56.9%
Internal rate of return-IRR | IRR % | 8.762%
What is the project net present value - NPV | NPV $ | 3382846.4805
Difference grant will make to project in terms of scale & timing (simple payback) | Years | 9
Production Unit (PU) / Manufacturing facility | PU | Tonnes of cement produced
Emissions reduction per production unit / manufacturing facility | T CO2-e/PU | 1.58
Cost Reduction per production unit / manufacturing facility | $/PU | 2.8
Total Cost Saving | $/year | 140000
11. CIGP feasibility parameters | Units | Amount
Minimum CIGP funding | $ | 50000
Maximum CIGP funding | $ | 500000
Maximum CIGP funding of eligible costs | % | 50%
Maximum years to spend CIGP funds | years | 2
12. Project assumptions
Assumptions and Factors | Units | Amount | Source or reasoning behind value (Attach clearly labelled evidence in SmartyGrants where needed)
Project start date | Date | 2027-07-01
Project life | Months | 22
Threshold return rate for investment (IRR) | % | 5%
Other revenue | $/year | 5 | Premium price per tonne for carbon neutral cement
Production Unit (PU) | PU | Tonnes of cement produced | Production unit is a way of measuring output.
Mobile Plant emissions (diesel) | T CO2e/KL | 2.7174 | National Greenhouse Account Factors 2024
Mobile Plant emissions (petrol) | T CO2e/KL | 2.3803 | National Greenhouse Account Factors 2024
Stationary Plant emissions (diesel) | T CO2e/KL | 2.7097 | National Greenhouse Account Factors 2024
Fugitive emissions | T CO2e/T | 3.759 | National Greenhouse Account Factors 2024
Process emissions | T CO2e/T | 0.535 | National Greenhouse Account Factors 2024
Electricity emissions Factor Scope 2 | T | 0.68 | National Greenhouse Account Factors 2024
Natural Gas emissions Factor Scope 1 | T CO2e/GJ | 0.05153 | National Greenhouse Account Factors 2024
Amount of Electricity per PU | MWH/PU | 0.5 | Project specific (not used in case example)
Amount of Natural Gas per PU | GJ/PU | 1.03 | Project specific
Cost to flare emissions | $/T Flared | 2 | Project specific
Diesel cost | $/KL | 1947.8 | Terminal Gate Price (Min) 11 May 22
Petrol cost | $/KL | 1725.5 | ULP Terminal Gate Price (Min) 11 May 22
Gas cost | $/GJ | 10.48 | From WOSP 23-24 modelled price
Electricity cost | $/MWh | 30 | Renewables PPA
Carbon credit generation cost | $/T CO2e | 0.5 | Monitoring and reporting cost
Carbon credit purchase cost | $/T CO2e | 30 | Spot market price
Current production volume per annum | PU/year | 50000 | Tonnes of cement
Minimum permanence of abatement (years) | years | 10
Note on A50: The minimum rate of return your organisation would need to proceed with a project of this size and risk profile.
NOTE!
All case study numbers are fictional and may not represent a real world scenario in terms of potential emissions reduction and financial costs or savings. The case study is only designed as an example of how to use the Financial Model template and should not be used as a basis for a grant application.

## In-kind contributions
Carbon Innovation Grants Program Feasibility Studies Round 3 - 2026
Please describe the in-kind contributions you plan to make along with the financial value of each
In-kind contributions from applicant
In-kind materials or goods |  | In-kind labour or services
Contribution (description of goods to be provided) | Value in dollars | Contribution (description of services to be provided) | Role | hours | Rate ($/h) | Total Costs ($)
Total in-kind materials or goods | 0 | Total in-kind labour or services |  |  |  | 0
Total in kind contributions from applicant | 0
In-kind contributions from others
In-kind materials or goods |  | In-kind labour or services
Contribution (description of goods to be provided) | Value in dollars | Contribution (description of services to be provided) | Role | hours | Rate ($/h) | Total Costs ($)
|  | Design a shed | Planner | 2 | 150 | 300
Total in-kind materials or goods | 0 | Total in-kind labour or services |  |  |  | 300
Total in kind contributions from others | 300
Total in kind contributions from applicant and others | 300

## Merit Criteria
Carbon Innovation Grants Program Feasibility Studies Round 3 - 2026
Merit Category | Weighting | Merit Criteria | Financial Model Spreadsheet | Applicant Reports, Studies, and/or Response in SmartyGrants | Financial Model Evidence Reference
Merit 1 Reducing emissions | 30% | The direct and indirect greenhouse gas emission reductions likely to be achieved | P | P | Outputs and Inputs - 10. Project Summary
|  | The scale of potential emissions reduction relative to baseline emissions from the heavy industry operations | P | P | Outputs and Inputs - 10. Project Summary
|  | The permanence of the potential emissions reduction |  | P
|  | How the Carbon Mitigation Hierarchy and the transition to net zero emissions has been considered in project design |  | P
|  | The target cost ($ per tonne) of carbon dioxide equivalent emissions reduction. | P | P | Outputs and Inputs - 10. Project Summary
Merit 2 Business case | 20% | The amount of funding sought for the project and the total project cost | P | P | Outputs and Inputs - 10. Project Summary
|  | The other expected sources of funding and evidence that funding has been, or has a reasonable chance of being, secured | P | P | Project Model - 2 Project Funding
|  | The proportion of total funds including in-kind contributions committed by the applicant (excluding other grants) | P | P | Project Model - 2 Project Funding & Outputsand Inputs - 10. Project Summary
|  | The demonstrated financial capacity of the applicant to fund its contribution to the costs of the project. Financial capacity and ability to secure funding to implement the project (attach audited balance sheet of the past two years) |  | P
|  | Justification for the need for Government assistance by presenting the: | P | P | Project Model - 6 Financial return and Outputs and Inputs - 10. Project Summary
i. likelihood that the project would not proceed without the funding requested
ii. status of the project (whether the project has commenced)
iii. difference the grant will make to the project in terms of scale and timing.
|  | The project’s technical feasibility and likelihood of success |  | P
|  | Commitment to proceed to build the project if it is proven feasible, including an understanding of the likely cost and benefits of deploying the project at full scale. | P | P | Project Model - 6 Financial return and Outputs and Inputs - 10. Project Summary
Merit 3 Ability to Deliver | 15% | Technical and management capability and expertise of the applicant. |  | P
|  | Roles of project partners and the status of any relevant agreements between project partners, including the level of involvement of one or more heavy industry in the project. |  | P
|  | Governance and or organisational structure for delivery of the project. |  | P
|  | A comprehensive delivery plan for the project, including such things as: timeframe for project commencement and delivery, budget and procurement, project milestones and performance criteria, resourcing and quality assurance. | P | P | Outputs and Inputs - 10. Project Summary
|  | A completed risk register template. |  | P
|  | A clear and detailed funding strategy demonstrating a path to achieving financial close and commencing project delivery upon execution of a Funding Agreement. |  | P
|  | The applicant has secured or can secure the required regulatory approvals and/or access permits to carry out the project. |  | P
|  | Current insurance where relevant or plans for insurance to cover potential liability that may result from carrying out the project. |  | P
Merit 4 Innovation and potential for wider adoption | 20% | Project innovation – such as a world, national, state or industry sector first, or not common practice (the degree of innovation and/or the extension of the project beyond ‘common practice’ in Western Australia for the relevant sector or subsector and not something that is a requirement under Australian or state law) |  | P
|  | The likelihood that the project will result in similar projects being implemented by the applicant or by others, multiplying the emissions reduction potential |  | P
|  | The potential for cost reductions for future projects by demonstration of new technology, including the ability of future projects to be financially viable without grant funding |  | P
|  | The scale of potential abatement if the technology was adopted throughout the industry sector in WA and more broadly | P | P | Outputs and Inputs - 10. Project Summary
|  | The potential for further research or studies arising from the project |  | P
|  | An assessment of project competitiveness against alternatives, including similar technologies or methods in development. |  | P
|  | Demonstrated benefits to heavy industry and mitigating hard-to-abate emissions. |  | P
Merit 5 Public Good | 15% | Knowledge sharing – describe the type, quality and extent of the knowledge sharing information about, and resulting from, the project that the applicant proposes to make publicly available to build capacity amongst others, support learning-by-doing and/or demonstrate the feasibility of new technologies or processes |  | P
|  | Economic development – delivering economic benefits to the state (i.e. the number of jobs expected to be created by the project, benefits to Aboriginal and Torres Strait Islander employment and/or the extent to which the project represents a new industry or business practice in the state) |  | P
|  | Environmental co-benefits of the project, such as reduced pollution, reduction in the use of raw materials, climate adaptation/resilience, or benefits to local or regional biodiversity |  | P
"Economic participation and development of Aboriginal and Torres Strait Island people, including: (i) seeking their knowledge and involvement in decision making (about land, culture and traditional practices, wherever applicable); (ii) increasing the proportion of services sought from Aboriginal-led organisations; (iii) improving the percentage of Aboriginal workforce and ensure wage parity (iv) training and capacity building for Aboriginal-led organisations"
|  | Project contribution to the objectives of the WA Climate Policy. |  | P

## Eligible costs
Carbon Innovation Grants Program Feasibility Studies Round 3 - 2026
Eligible costs include:
· | capital costs of equipment used for carbon abatement or sequestration
· | essential enabling equipment such as energy storage, feedstock storage, pumps, tanks, system control equipment, system power or energy conversion equipment, pipework, monitoring or communications equipment and structures used for housing power-system equipment
· | essential non-equipment expenditure including design, professional services, transport, installation and commissioning, laboratory testing, field sampling, related to the attainment of a project objective or milestone
· | project management costs and grant administration costs.
An in-kind contribution is any non-monetary contribution of goods or services for the project by the applicant. Eligible in-kind contributions from the applicant can cover any of the listed types of eligible project costs. In-kind contributions must be described with sufficient detail to enable assessment of whether the valuation is reasonable, this is described further in the Financial Model template.
The above lists of eligible and ineligible costs identify the most common examples and are not intended to be prescriptive or comprehensive. If there is any doubt about eligibility of costs, please contact: carbongrants@dwer.wa.gov.au
Generally ineligible costs include:
· | land acquisition
· | venture capital expenditure to third parties
· | purchase of carbon credits to achieve a net emissions reduction
· | legal costs such as those associated with preparing grant applications, finalising, or managing compliance with a funding agreement
· | statutory permit or licence costs
· | costs associated with core business or business as usual activities
· | ongoing administrative and operational costs including rent, electricity and salaries of existing staff working their usual hours and duties
· | projects that seek retrospective funding for work already undertaken
· | works already underway or completed at the time the funding was announced (including but not limited to contracts already in place to construct infrastructure or buy equipment or where construction has commenced)
· | ongoing maintenance of projects to which organisations have committed as part of a previous grant
· | costs of preparing applications, reports or associated supporting material.

## Milestone table (hidden)
Key deliverables | Completion date | Expected eligible expenditure to complete milestone | Percentage of reimbursement of actual Eligible Expenditure for each Milestone | Anticipated Milestone Payment | Months from project start to milestone completion
#REF! | #REF! | #REF! |  | #REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF!
#REF!
#REF!

## Glossary
Carbon Innovation Grants Program Feasibility Studies Round 3 - 2026
Term | Definition
Application | An application made to the Government of Western Australia for funding under the program, which includes a project proposal, a completed application form and any other supporting or additional information provided by the applicant in relation to the application.
Assessment Panel | The program’s Executive Group (see below) in its capacity of assessing applications to the program and finalising a recommendations report, supported by non-voting administrative members and probity advisory members.
AWST | Australian Western Standard Time
Baseline | The annual Scope 1, 2 and/or 3 greenhouse gas emissions of a facility, or facilities, as defined by the Clean Energy Regulator, prior to undertaking a carbon emissions reduction project.
Carbon Credits (Carbon Farming Initiative) Act 2011 | This Act establishes the Australian Carbon Credit Unit (ACCU) Scheme to support projects that avoid the release of greenhouse gas emissions or remove and sequester carbon from the atmosphere in accordance with approved methodologies.
Carbon emissions reduction project | A project that deploys or applies a technology that achieves a net reduction in greenhouse gas emissions to the atmosphere through one or more of the following: *Avoiding emissions (e.g. by changing an industrial process so that it no longer produces emissions) *Reducing emissions (e.g. by improving industrial process efficiency) *Capturing and permanently storing greenhouse gases (e.g. by storing within an underground reservoir, solid form, or carbon farming methods).
Carbon mitigation hierarchy | The process of reducing carbon emissions through the most efficient means available, in order of priority: avoid > reduce > store > offset.
CCS | Carbon capture and storage
CCUS | Carbon Capture, Use and Storage
CIGP | Carbon Innovation Grants Program
CIGP applicant guidelines | This document setting out the guidance and information necessary for applicants to apply to the program.
Clean Energy Regulator | The Australian national regulator responsible for administering the Carbon Farming Initiative, the Emissions Reduction Fund and the methods for the issue of Australian Carbon Credit Units.
Commercial Readiness Level (CRL) | Defined stages in the commercialisation of a technology from early research, through to real- world testing, pilot and full-scale deployment, as defined by the Australian Renewable Energy Agency (ARENA).
Conditions Precedent | A condition or conditions of the funding agreement, typically requiring evidence that the grant recipient has secured the balance of funding for the total cost of the grant funded project. This is required before any grant funding can be paid.
DWER, the department | Department of Water and Environmental Regulation
Eligible costs | Those costs referred to in section 4 of these Applicant guidelines
Executive Group | Nominated representatives from DWER that oversee and approve key aspects of program administration and provide advice and recommendations to the Minister for Energy and Decarbonisation
Full-scale deployment | As it relates to the CIGP, a carbon emission reduction project that is applied to an industrial facility or process to the maximum extent practicable.
Funding agreement | The contract for funding entered between a successful applicant and the Government of Western Australia to perform the project.
GST | Goods and Services Tax
Heavy industry | Heavy industry, as referenced in the CIGP objectives and merit criteria, is a general term that can cover many types of businesses involved in industrial processing of materials, mining or manufacturing. For example, stationary and mobile plant servicing heavy industry, mineral extraction, mineral or metal refining, machinery manufacturing, fuel production or chemical/fertiliser manufacturing. The following classifications can also be used as a guide to identify heavy industries that are the focus of the CIGP: *Emissions Intensive Trade Exposed Industries as defined by Schedule six of the Renewable Energy (Electricity) Regulations 2001 as amended and in force at the time of grant application *Hard to abate’ industries including iron and steel, aluminium, chemicals (ammonia, fertilisers and explosives), LNG and ‘Other metals’ identified in the Australian Industry Energy Transitions Initiative Phase 1 Technical Report 2021, ClimateWorks Australia, Butler, C, Maxwell, R, Graham, P & Hayward, J. *Designated large facilities as defined by the National Greenhouse and Energy Reporting Act 2007 as amended and in force at the time of grant application.
Industrial business/activity | An otherwise eligible entity or organisation which is involved in the production of goods and/or industrial processing of materials.
IRR | Internal rate of return - measures the financial return from doing the project
Lead applicant | The applicant that signs the application form and subsequent funding agreement and the recipient of the grant funding if successful.
Milestone | Represents the completion of a major step in the project that requires the commitment of a certain amount of time, resources and effort.
Milestone Payment | Means an instalment of the Funding determined in accordance with clause 3.4 of the Funding Agreement.
NGAF | Australian National Greenhouse Accounts Factors
NGER | National Greenhouse and Energy Reporting Scheme
Nominal and real rates | Nominal interest rates, rates of return etc., include inflation. e.g., if I put $100 in the bank at an advertised (nominal) rate of 5% per year, and in one year I have $105 of next year's dollars, while inflation has removed say 3% of the value, for a real rate of 2%. This financial model works on real rates and current year dollars.
NPV | Net Present Value - the value in current dollars of the project
Payback | The number of years until a project has earned its construction cost.
Permanence | The permanence of carbon abatement resulting from a project. This can include permanence of emissions reductions relative to a baseline or the permanence of a long-term carbon storage activity. CIGP expectations of permanence are aligned with definitions used by the Clean Energy Regulator.
Program | The Carbon Innovation Grants Program established in accordance with the Financial Management Act 2006.
Project | The carbon emissions reduction project that is the subject of the application to the program.
Scope 1 | Greenhouse gas emissions released to the atmosphere as a direct result of an activity
Scope 2 | Emissions released to the atmosphere indirectly from the consumption of an energy commodity
Scope 3 | Indirect greenhouse gas emissions other than scope 2 emissions that are generated in the wider economy
Secondary applicant | Applicants that are listed in the application as part of a consortium or partnership, who are not the Lead applicant.
SMC | Safeguard Mechanism Credits - proposed tradeable credits for exceeding Safeguard Mechanism targets.
Technology Readiness Level (TRL) | Defined stages in the development of a technology from early research, through to real world testing and pilot and full scale deployment, as defined by the Australian Renewable Energy Agency (ARENA)
WA | Western Australia